## Iowa_BLE_Tracking
| HUC8 | which_grid | Name | PBL_Assign | P01_MM | RAW_Grd_MM | DFIRM_Grd_MM | Addl_Grd_MM | Prod Stage | P01 Analyst | AECOM Tie-in | Name__HUC8 | TO_Area | Model Complete | Contractor | Phase 2 Step | loc_id | Grid Notes
0 | 07060001 | 1, 2 | Coon-Yellow | QB | 2023-11-30 | 2024/02/23 | 0000/00/00 | 0000/00/00 | Phase 2 Spatial | Matt | NO | Coon-Yellow | FY20_1A | 2023-10-12 | AtkinsRealis | 1 | 1 | TODO: DRAFT, Addl Grids
1 | 07060002 | 2 | Upper Iowa | MB | 2023-11-30 | 2024/02/23 | 2024/03/10 | 0000/00/00 | Phase 2 Spatial | Reina | NO | Upper Iowa | FY20_1A | 2023-10-12 | AtkinsRealis | 1 | 2 | TODO: DRAFT, Addl Grids
2 | 07060004 | All on MM | Turkey | EC | 2024-05-22 | 2024/04/15 | 2024/08/13 | 2024/05/22 | Phase 2 Spatial | Multi | NO | Turkey | FY20_1A | 2023-11-11 | AtkinsRealis | 1 | 3 | UPDATE: DFIRM grid extents
3 | 07060006 | All on MM | Maquoketa | RK | 2024-05-22 | 2024/05/17 | 2024/05/21 | 2024/05/21 | Phase 2 Spatial | Multi | NO | Maquoketa | FY20_1A | 2023-12-12 | AtkinsRealis | 1 | 4
4 | 07080102 | All on MM | Upper Wapsipinicon | AE | 2023-12-30 | 2024/04/15 | 2024/08/14 | 2024/05/22 | Phase 2 Spatial | Matt | YES | Upper Wapsipinicon | FY20_1A | 2023-11-11 | AtkinsRealis | 1 | 5 | UPDATE: DFIRM Clipped
5 | 07080103 | All on MM | Lower Wapsipinicon | MT | 2024-05-22 | 2024/05/09 | 2024/08/14 | 2024/05/22 | Phase 2 Spatial | Matt | NO | Lower Wapsipinicon | FY20_1A | 2024-01-10 | AtkinsRealis | 1 | 6 | UPDATE: DFIRM grid extents
6 | 07080105 | 2 | South Skunk |  | 2024-06-03 | 2024/03/05 | 2024/06/17 | 0000/00/00 | Phase 1 Delivered | Erika | YES | South Skunk | FY21_2A | 2023-11-11 | AtkinsRealis |  | 7
7 | 07080206 | All on MM | Lower Cedar | QB | 2024-07-13 | 2024/06/14 | 2024/07/16 | 2024/07/18 | Phase 2 Spatial | Reina | YES | Lower Cedar | FY20_1A | 2024-05-31 | AtkinsRealis | 1 | 8
8 | 07100006 | 1, 2 | North Raccoon |  | 2024-02-26 | 2024/02/13 | 0000/00/00 | 0000/00/00 | Phase 1 Delivered | YES | YES | North Raccoon | FY21_2A | 2023-08-12 | AtkinsRealis |  | 9
9 | 07100007 | 1, 2 | South Raccoon |  | 2023-07-30 | 2023/08/31 | 0000/00/00 | 0000/00/00 | Phase 1 Delivered | YES | YES | South Raccoon | FY21_2A | 2023-06-11 | AtkinsRealis |  | 10 | TODO: RAW, DRAFT, Addl
10 | 07100008 | 1, 2 | Lake Red Rock |  | 2023-12-30 | 2024/03/24 | 0000/00/00 | 0000/00/00 | Phase 1 Delivered | Reina | YES | Lake Red Rock | FY21_2A | 2023-11-11 | AtkinsRealis |  | 11
11 | 07100009 | 1, 2 | Lower Des Moines |  | 2024-08-04 | 2024/08/04 | 0000/00/00 | 0000/00/00 | Phase 1 Delivered | R+E | YES | Lower Des Moines | FY21_2A | 2024-07-25 | AtkinsRealis |  | 12
12 | 10230002 | 1, 2 | Floyd |  | 2024-07-10 | 2024/07/12 | 0000/00/00 | 0000/00/00 | Phase 1 Delivered | Reina | NO | Floyd | FY22_3B | 2024-07-08 | AtkinsRealis |  | 13
13 | 10230003 | 1, 2 | Little Sioux |  | 2024-08-05 | 2024/08/07 | 0000/00/00 | 0000/00/00 | Phase 1 Delivered | E + M | YES | Little Sioux | FY22_3B | 2024-07-16 | AtkinsRealis |  | 14
14 | 10230004 | 1, 2 | Monona-Harrison Ditch |  | 2024-08-01 | 2024/08/01 | 0000/00/00 | 0000/00/00 | Phase 1 Delivered | Reina | NO | Monona-Harrison Ditch | FY22_3B | 2024-03-12 | AtkinsRealis |  | 15
15 | 10230005 | 1, 2 | Maple |  | 2024-07-11 | 2024/06/12 | 0000/00/00 | 0000/00/00 | Phase 1 Delivered | Erika | NO | Maple | FY22_3B | 2024-07-08 | AtkinsRealis |  | 16
16 | 10230007 | 1, 2 | Boyer |  | 2024-07-30 | 2024/07/30 | 0000/00/00 | 0000/00/00 | Phase 1 Delivered | Reina | YES | Boyer | FY22_3B | 2024-07-21 | AtkinsRealis |  | 17
17 | 07060005 | All on MM | Apple-Plum | MB | 2024-02-28 | 2024/04/04 | 2024/04/05 | 2024/04/05 | Phase 2 Spatial | Erika | NO | Apple-Plum | FY20_1A | 2024-01-10 | AtkinsRealis | 1 | 18
18 | 07080201 | 2 | Upper Cedar | RK | 2023-12-30 | 2024/03/15 | 2024/08/15 | 0000/00/00 | Phase 2 Validation | Matt | YES | Upper Cedar | FY20_1A | 2023-11-11 | AtkinsRealis | 3 | 19 | UPDATE: DFIRM, TODO: Add'l
19 | 10170204 | All on MM | Rock |  | 2024-05-29 | 2024/05/28 | 2024/05/29 | 2024/05/29 | Draft DFIRM Submitted | Matt | NO | Rock | FY22_3B | 2024-02-10 | AtkinsRealis |  | 20
20 | 10230001 | 1, 2 | Blackbird-Soldier |  | 2024-08-13 | 2024/08/06 | 0000/00/00 | 0000/00/00 | Mapping In-Progress | Erika | NO | Blackbird-Soldier | FY22_3B | 2024-04-11 | AtkinsRealis |  | 21
21 | 10230006 | 1, 2 | Big Papillion-Mosquito |  | 2024-08-05 | 2024/08/06 | 0000/00/00 | 0000/00/00 | Mapping In-Progress | Reina | YES | Big Papillion-Mosquito | FY22_3B | 2024-05-12 | AtkinsRealis |  | 22
22 | 10170203 | All on MM | Lower Big Sioux |  | 2024-03-30 | 2024/05/24 | 2024/06/26 | 2024/05/24 | Draft DFIRM Submitted | Matt | NO | Lower Big Sioux | FY22_3B | 2024-02-10 | AtkinsRealis |  | 23
23 | 07060003 | All on MM | Grant-Little Maquoketa | MT | 2024-01-30 | 2024/03/15 | 2024/06/26 | 2024/05/22 | Phase 2 Spatial | Erika | NO | Grant-Little Maquoketa | FY20_1A | 2023-12-12 | AtkinsRealis | 1 | 24
24 | 07080101 | All on MM | Copperas-Duck | MT | 2024-03-30 | 2024/04/20 | 2024/04/20 | 2024/05/01 | Phase 2 Spatial | Reina | YES | Copperas-Duck | FY20_1A | 2024-02-10 | AtkinsRealis | 1 | 25
25 | 07110001 | All on MM | Bear-Wyaconda |  | 2024-02-28 | 2024/03/26 | 2024/03/26 | 2026/03/28 | Phase 1 Delivered | Reina | YES | Bear-Wyaconda | FY21_2A | 2024-01-10 | AtkinsRealis |  | 26
26 | 07110001 | All on MM | Bear-Wyaconda |  | 2024-02-28 | 2024/03/26 | 2024/03/26 | 2026/03/28 | Phase 1 Delivered | Reina | YES | Bear-Wyaconda | FY21_2A | 2024-01-10 | AtkinsRealis |  | 26