## Tracking_Main
Delivery Area Info |  |  | MIP Task Status |  |  | Model Manager Uploads |  |  |  |  | Overall | Details |  |  |  | Other
HUC8 | Name | TO_Area | Draft | Floodplain | Hydraulics | P01 GDB | RAW Grids | DFIRM Grids | Additional Grids | Missing Grids | Prod Stage | P01 Analyst | Model Complete | FRP % | Notes | Has AECOM Tie | MIP_Case
07060001 | Coon-Yellow | FY20_1A | Approved | Submitted | Approved | 2023/11/30 | 2024/02/23 | 2024/08/20 | 2024/08/20 | All on MM | Pass 2/2 | Matt | 2023/10/12 | 100 | Passed MIP Validation | NO | 21-07-0002S
07060002 | Upper Iowa | FY20_1A | Approved | Submitted | Approved | 2023/11/30 | 2024/02/23 | 2024/03/10 | 2024/08/20 | All on MM | Pass 1/2 | Reina | 2023/10/12 | 100 | Passed MIP Validation; Round 2 Validation 10/11/2024 | NO | 21-07-0002S
07060004 | Turkey | FY20_1A | Approved | Submitted | Approved | 2024/05/22 | 2024/04/15 | 2024/08/27 | 2024/05/22 | All on MM | Pass 2/2 | Multi | 2023/11/11 | 100 | Passed MIP Validation | NO | 21-07-0002S
07060006 | Maquoketa | FY20_1A | Approved | Submitted | Approved | 2024/05/22 | 2024/05/17 | 2024/05/21 | 2024/05/21 | All on MM | Pass 1/2 | Multi | 2023/12/12 | 100 | Passed MIP Validation; Round 2 Validation 10/11/2024 | NO | 21-07-0002S
07080102 | Upper Wapsipinicon | FY20_1A | Approved | Submitted | Approved | 2023/12/30 | 2024/04/15 | 2024/08/14 | 2024/05/22 | All on MM | Pass 2/2 | Matt | 2023/11/11 | 100 | Passed MIP Validation | YES | 21-07-0002S
07080103 | Lower Wapsipinicon | FY20_1A | Approved | Submitted | Approved | 2024/05/22 | 2024/05/09 | 2024/08/14 | 2024/05/22 | All on MM | Pass 1/2 | Matt | 2024/01/10 | 100 | Passed MIP Validation; Round 2 Validation 10/11/2024 | NO | 21-07-0002S
07080105 | South Skunk | FY21_2A | Next | Next | Next | 2024/06/03 | 2024/03/05 | 2024/06/17 |  | 2 | Phase 1 | Erika | 2023/11/11 | 0 |  | YES | 22-07-0035S
07080206 | Lower Cedar | FY20_1A | Approved | Submitted | Approved | 2024/07/13 | 2024/06/14 | 2024/07/16 | 2024/07/18 | All on MM | Pass 1/2 | Reina | 2024/05/31 | 100 | Passed MIP Validation; Round 2 Validation 10/11/2024 | YES | 21-07-0002S
07100006 | North Raccoon | FY21_2A | Next | Next | Next | 2024/02/26 | 2024/02/13 |  |  | 1, 2 | Phase 1 | YES | 2023/08/12 | 0 |  | YES | 22-07-0035S
07100007 | South Raccoon | FY21_2A | Next | Next | Next | 2023/07/30 | 2023/08/31 |  |  | 1, 2 | Phase 1 | YES | 2023/06/11 | 0 | TODO: RAW, DRAFT, Addl | YES | 22-07-0035S
07100008 | Lake Red Rock | FY21_2A | Next | Next | Next | 2023/12/30 | 2024/03/24 |  |  | 1, 2 | Phase 1 | Reina | 2023/11/11 | 0 |  | YES | 22-07-0035S
07100009 | Lower Des Moines | FY21_2A | Next | Next | Next | 2024/08/04 | 2024/08/04 | 2024/11/20 |  | 1, 2 | Phase 1 | R+E | 2024/07/25 | 0 |  | YES | 22-07-0035S
10230002 | Floyd | FY22_3B | Approved | Submitted | Submitted | 2024/09/09 | 2024/07/12 | 2024/09/10 | 2024/09/12 | All on MM | Pass 1/2 | Erika, Reina | 2024/07/08 | 100 | All Hydraulics Spatial Files uploaded 10/16 | NO | 23-07-0037S
10230003 | Little Sioux | FY22_3B | Submitted | Submitted | Submitted | 2024/08/05 | 2024/08/07 | 2024/10/15 | 2024/10/15 | All on MM | Pass 1/2 | E + M | 2024/07/16 | 100 | All Hydraulics Spatial Files uploaded 10/16 | YES | 23-07-0037S
10230004 | Monona-Harrison Ditch | FY22_3B | Approved | Submitted | Submitted | 2024/08/01 | 2024/08/01 | 2024/10/07 | 2024/10/10 | All on MM | Pass 1/2 | Reina | 2024/03/12 | 100 | All Hydraulics Spatial Files uploaded 10/16 | NO | 23-07-0037S
10230005 | Maple | FY22_3B | Approved | Submitted | Submitted | 2024/07/11 | 2024/06/12 | 2024/10/16 | 2024/10/16 | All on MM | Pass 1/2 | Erika | 2024/07/08 | 100 | MIP Exception; All Hydraulics Spatial Files uploaded 10/16 | NO | 23-07-0037S
10230007 | Boyer | FY22_3B | Submitted | Submitted | Submitted | 2024/07/30 | 2024/07/30 | 2024/10/15 | 2024/10/15 | All on MM | Pass 1/2 | Reina | 2024/07/21 | 100 | All Hydraulics Spatial Files uploaded 10/16 | YES | 23-07-0037S
07060005 | Apple-Plum | FY20_1A | Approved | Submitted | Approved | 2024/02/28 | 2024/04/04 | 2024/04/05 | 2024/04/05 | All on MM | Pass 2/2 | Erika | 2024/01/10 | 100 | TODO: Missing 0.2% Vel grid | NO | 21-07-0002S
07080201 | Upper Cedar | FY20_1A | Approved | Submitted | Approved | 2023/12/30 | 2024/03/15 | 2024/08/15 | 2024/08/19 | All on MM | Pass 2/2 | Matt | 2023/11/11 | 100 | Passed MIP Validation | YES | 21-07-0002S
10170204 | Rock | FY22_3B | Submitted | Submitted | In Backcheck | 2024/05/29 | 2024/05/28 | 2024/05/29 | 2024/05/29 | All on MM | Pass 1/2 | Matt | 2024/02/10 | 100 | All Hydraulics Spatial Files uploaded 10/16 | NO | 23-07-0036S
10230001 | Blackbird-Soldier | FY22_3B | Submitted | Submitted | Submitted | 2024/08/20 | 2024/08/06 | 2024/10/10 | 2024/10/10 | All on MM | Pass 1/2 | Erika | 2024/08/01 | 100 | All Hydraulics Spatial Files uploaded 10/16 | NO | 23-07-0037S
10230006 | Big Papillion-Mosquito | FY22_3B | Submitted | Submitted | Submitted | 2024/08/05 | 2024/08/06 | 2024/10/07 | 2024/10/08 | All on MM | Pass 1/2 | Reina | 2024/05/12 | 100 | All Hydraulics Spatial Files uploaded 10/16 | YES | 23-07-0037S
10170203 | Lower Big Sioux | FY22_3B | Submitted | Submitted | In Backcheck | 2024/03/30 | 2024/05/24 | 2024/06/26 | 2024/05/24 | All on MM | Pass 1/2 | Matt | 2024/02/10 | 100 | All Hydraulics Spatial Files uploaded 10/16 | NO | 23-07-0036S
07060003 | Grant-Little Maquoketa | FY20_1A | Approved | Submitted | Approved | 2024/01/30 | 2024/03/15 | 2024/06/26 | 2024/05/22 | All on MM | Pass 2/2 | Erika | 2023/12/12 | 100 | Passed MIP Validation | NO | 21-07-0002S
07080101 | Copperas-Duck | FY20_1A | Approved | Submitted | Approved | 2024/03/30 | 2024/04/20 | 2024/04/20 | 2024/05/01 | All on MM | Pass 2/2 | Reina | 2024/02/10 | 100 | Passed MIP Validation | YES | 21-07-0002S
07110001 | Bear-Wyaconda | FY21_2A | Next | Next | Next | 2024/02/28 | 2024/03/26 | 2024/03/26 | 2024/03/26 | All on MM | Phase 1 | Reina | 2024/01/10 | 0 |  | YES | 22-07-0035S

## Sheet1
HUC8 | Name | TO_Area | Draft | Floodplain | Hydraulics | P01 GDB | RAW Grids | DFIRM Grids | Additional Grids | Missing Grids | Prod Stage | P01 Analyst | Model Complete | FRP % | Notes | Has AECOM Tie | MIP_Case |  | Source Columns | Target Name | HUC8
[19 empty] | HUC8 | HUC8 | Draft_MIP
[19 empty] | Draft_MIP | Name | FP_MIP
[19 empty] | FP_MIP | TO_Area | FRP
[19 empty] | FRP | Draft | BFE_TODO
[19 empty] | BFE_TODO | Floodplain | P02a_Assign
[19 empty] | P02a_Assign | Hydraulics | P01_MM
[19 empty] | P01_MM | P01 GDB | Hydra_MIP
[19 empty] | Hydra_MIP | RAW Grids | which_grid
[19 empty] | which_grid | DFIRM Grids | Name
[19 empty] | Name | Additional Grids | Has AECOM Tie
[19 empty] | Has AECOM Tie | Missing Grids | RAW_Grd_MM
[19 empty] | RAW_Grd_MM | Prod Stage | DFIRM_Grd_MM
[19 empty] | DFIRM_Grd_MM | P01 Analyst | Addl_Grd_MM
[19 empty] | Addl_Grd_MM | Model Complete | Prod Stage
[19 empty] | Prod Stage | FRP % | P01 Analyst
[19 empty] | P01 Analyst | Notes | TO_Area
[19 empty] | TO_Area | Has AECOM Tie | Model Complete
[19 empty] | Model Complete | MIP_Case | Notes
[19 empty] | Notes |  | MIP_Case
[19 empty] | MIP_Case |  | FRP_Perc_Complete
FRP_Perc_Complete
HUC8 | Draft_MIP | FP_MIP | FRP | BFE_TODO | P02a_Assign | P01_MM | Hydra_MIP | which_grid | Name | Has AECOM Tie | RAW_Grd_MM | DFIRM_Grd_MM | Addl_Grd_MM | Prod Stage | P01 Analyst | TO_Area | Model Complete | Notes | MIP_Case | FRP_Perc_Complete