## Tracking_Main
HUC8 | FRP | P02a_Assign | P01_MM | Name | RAW_Grd_MM | DFIRM_Grd_MM | Addl_Grd_MM | Prod Stage | P01 Analyst | AECOM Tie-in | TO_Area | Model Complete | Notes | which_grid | Addl_Gri_1 | FRP_Perc_Complete
07060001 | WSE/Depth; CSLF; PAC; Velocity | QB | 11/30/2023 | Coon-Yellow | 2024/02/23 | 2024/08/20 | 2024/08/20 | Pass 2/2 | Matt |  | FY20_1A | 10/12/2023 | Passed MIP Validation | All on MM | 2024/08/20 | 100
07060002 | WSE/Depth; CSLF; PAC; Velocity | MB | 11/30/2023 | Upper Iowa | 2024/02/23 | 2024/03/10 | 2024/08/20 | Pass 2/2 | Reina |  | FY20_1A | 10/12/2023 | Passed MIP Validation | All on MM | 2024/08/20 | 100
07060004 | WSE/Depth; CSLF; PAC; Velocity | EC | 5/22/2024 | Turkey | 2024/04/15 | 2024/08/27 | 2024/05/22 | Pass 2/2 | Multi |  | FY20_1A | 11/11/2023 | Passed MIP Validation | All on MM | 2024/05/22 | 100
07060006 | WSE/Depth; CSLF; PAC; Velocity | RK | 5/22/2024 | Maquoketa | 2024/05/17 | 2024/05/21 | 2024/05/21 | Pass 2/2 | Multi |  | FY20_1A | 12/12/2023 | Passed MIP Validation | All on MM | 2024/05/21 | 100
07080102 | WSE/Depth; CSLF; PAC; Velocity | KTG | 12/30/2023 | Upper Wapsipinicon | 2024/04/15 | 2024/08/14 | 2024/05/22 | Pass 2/2 | Matt |  | FY20_1A | 11/11/2023 | Passed MIP Validation | All on MM | 2024/05/22 | 100
07080103 | WSE/Depth; CSLF; PAC; Velocity | MT | 5/22/2024 | Lower Wapsipinicon | 2024/05/09 | 2024/08/14 | 2024/05/22 | Pass 2/2 | Matt |  | FY20_1A | 1/10/2024 | Passed MIP Validation | All on MM | 2024/05/22 | 100
07080105 |  |  | 6/3/2024 | South Skunk | 2024/03/05 | 2024/06/17 |  | Phase 1 | Erika |  | FY21_2A | 11/11/2023 |  | 2 |  | 0
07080206 | WSE/Depth; CSLF; PAC; Velocity | QB | 7/13/2024 | Lower Cedar | 2024/06/14 | 2024/07/16 | 2024/07/18 | Pass 2/2 | Reina |  | FY20_1A | 5/31/2024 | Passed MIP Validation | All on MM | 2024/07/18 | 100
07100006 |  |  | 2/26/2024 | North Raccoon | 2024/02/13 |  |  | Phase 1 | YES |  | FY21_2A | 8/12/2023 |  | 1, 2 |  | 0
07100007 |  |  | 7/30/2023 | South Raccoon | 2023/08/31 |  |  | Phase 1 | YES |  | FY21_2A | 6/11/2023 | TODO: RAW, DRAFT, Addl | 1, 2 |  | 0
07100008 |  |  | 12/30/2023 | Lake Red Rock | 2024/03/24 |  |  | Phase 1 | Reina |  | FY21_2A | 11/11/2023 |  | 1, 2 |  | 0
07100009 |  |  | 8/4/2024 | Lower Des Moines | 2024/08/04 |  |  | Phase 1 | R+E |  | FY21_2A | 7/25/2024 |  | 1, 2 |  | 0
10230002 |  | KTG | 9/9/2024 | Floyd | 2024/07/12 | 2024/09/10 | 2024/09/12 | Pass 1/2 | Erika, Reina |  | FY22_3B | 7/8/2024 | Passed MIP Validation | All on MM | 2024/09/12 | 0
10230003 |  | RK | 8/5/2024 | Little Sioux | 2024/08/07 | 2024/10/15 | 2024/10/15 | Pass 1/2 | E + M |  | FY22_3B | 7/16/2024 | Passed MIP Validation | 1, 2 | 2024/10/15 | 0
10230004 |  | MT | 8/1/2024 | Monona-Harrison Ditch | 2024/08/01 | 2024/10/07 | 2024/10/10 | Pass 1/2 | Reina |  | FY22_3B | 3/12/2024 | MIP Validation Passed | 1, 2 | 2024/10/10 | 0
10230005 |  | RK | 7/11/2024 | Maple | 2024/06/12 |  |  | Pass 1/2 | Erika |  | FY22_3B | 7/8/2024 | MIP Exception | 1, 2 |  | 0
10230007 |  | MT | 7/30/2024 | Boyer | 2024/07/30 |  |  | Pass 1/2 | Reina |  | FY22_3B | 7/21/2024 | Passed MIP Validation | 1, 2 |  | 0
07060005 | WSE/Depth; CSLF; PAC; Velocity | EC | 2/28/2024 | Apple-Plum | 2024/04/04 | 2024/04/05 | 2024/04/05 | Pass 2/2 | Erika |  | FY20_1A | 1/10/2024 | TODO: Missing 0.2% Vel grid | All on MM | 2024/04/05 | 100
07080201 | WSE/Depth; CSLF; PAC; Velocity | RK | 12/30/2023 | Upper Cedar | 2024/03/15 | 2024/08/15 | 2024/08/19 | Pass 2/2 | Matt |  | FY20_1A | 11/11/2023 | Passed MIP Validation | All on MM | 2024/08/19 | 100
10170204 |  |  | 5/29/2024 | Rock | 2024/05/28 | 2024/05/29 | 2024/05/29 | Pass 1/2 | Matt |  | FY22_3B | 2/10/2024 | Passed MIP Validation | All on MM | 2024/05/29 | 0
10230001 |  | RK | 8/20/2024 | Blackbird-Soldier | 2024/08/06 | 2024/10/10 | 2024/10/10 | Pass 1/2 | Erika |  | FY22_3B | 8/1/2024 | Passed MIP Validation | 1, 2 | 2024/10/10 | 0
10230006 |  | RK | 8/5/2024 | Big Papillion-Mosquito | 2024/08/06 | 2024/10/07 | 2024/10/08 | Pass 1/2 | Reina |  | FY22_3B | 5/12/2024 | Passed MIP Validation | All on MM | 2024/10/08 | 0
10170203 |  |  | 3/30/2024 | Lower Big Sioux | 2024/05/24 | 2024/06/26 | 2024/05/24 | Pass 1/2 | Matt |  | FY22_3B | 2/10/2024 | Passed MIP Validation | All on MM | 2024/05/24 | 0
07060003 | WSE/Depth; CSLF; PAC; Velocity | MT | 1/30/2024 | Grant-Little Maquoketa | 2024/03/15 | 2024/06/26 | 2024/05/22 | Pass 2/2 | Erika |  | FY20_1A | 12/12/2023 | Passed MIP Validation | All on MM | 2024/05/22 | 100
07080101 | WSE/Depth; CSLF; PAC; Velocity | MT | 3/30/2024 | Copperas-Duck | 2024/04/20 | 2024/04/20 | 2024/05/01 | Pass 2/2 | Reina |  | FY20_1A | 2/10/2024 | Passed MIP Validation | All on MM | 2024/05/01 | 100
07110001 |  |  | 2/28/2024 | Bear-Wyaconda | 2024/03/26 | 2024/03/26 | 2026/03/28 | Phase 1 | Reina |  | FY21_2A | 1/10/2024 |  | All on MM | 2026/03/28 | 0

## Tracking_Main_values
HUC8 | Draft_MIP | FP_MIP | FRP | P02a_Assign | P01_MM | Name | Hydra_MIP | Prod Stage | RAW_Grd_MM | DFIRM_Grd_MM | Addl_Grd_MM | P01 Analyst | AECOM Tie-in | TO_Area | Model Complete | Notes | which_grid | FRP_Perc_Complete
07060001 | Approved | Submitted | WSE/Depth; CSLF; PAC; Velocity | QB | 11/30/2023 | Coon-Yellow | In Backcheck | Pass 2/2 | 2024/02/23 | 2024/08/20 | 2024/08/20 | Matt |  | FY20_1A | 10/12/2023 | Passed MIP Validation | All on MM | 100
07060002 | Approved | Submitted | WSE/Depth; CSLF; PAC; Velocity | MB | 11/30/2023 | Upper Iowa | In Backcheck | Pass 2/2 | 2024/02/23 | 2024/03/10 | 2024/08/20 | Reina |  | FY20_1A | 10/12/2023 | Passed MIP Validation | All on MM | 100
07060004 | Approved | Submitted | WSE/Depth; CSLF; PAC; Velocity | EC | 5/22/2024 | Turkey | In Backcheck | Pass 2/2 | 2024/04/15 | 2024/08/27 | 2024/05/22 | Multi |  | FY20_1A | 11/11/2023 | Passed MIP Validation | All on MM | 100
07060006 | Approved | Submitted | WSE/Depth; CSLF; PAC; Velocity | RK | 5/22/2024 | Maquoketa | In Backcheck | Pass 2/2 | 2024/05/17 | 2024/05/21 | 2024/05/21 | Multi |  | FY20_1A | 12/12/2023 | Passed MIP Validation | All on MM | 100
07080102 | Approved | Submitted | WSE/Depth; CSLF; PAC; Velocity | KTG | 12/30/2023 | Upper Wapsipinicon | In Backcheck | Pass 2/2 | 2024/04/15 | 2024/08/14 | 2024/05/22 | Matt |  | FY20_1A | 11/11/2023 | Passed MIP Validation | All on MM | 100
07080103 | Approved | Submitted | WSE/Depth; CSLF; PAC; Velocity | MT | 5/22/2024 | Lower Wapsipinicon | In Backcheck | Pass 2/2 | 2024/05/09 | 2024/08/14 | 2024/05/22 | Matt |  | FY20_1A | 1/10/2024 | Passed MIP Validation | All on MM | 100
07080105 | Next | Next |  |  | 6/3/2024 | South Skunk | Next | Phase 1 | 2024/03/05 | 2024/06/17 |  | Erika |  | FY21_2A | 11/11/2023 |  | 2 | 0
07080206 | Approved | Submitted | WSE/Depth; CSLF; PAC; Velocity | QB | 7/13/2024 | Lower Cedar | In Backcheck | Pass 2/2 | 2024/06/14 | 2024/07/16 | 2024/07/18 | Reina |  | FY20_1A | 5/31/2024 | Passed MIP Validation | All on MM | 100
07100006 | Next | Next |  |  | 2/26/2024 | North Raccoon | Next | Phase 1 | 2024/02/13 |  |  | YES |  | FY21_2A | 8/12/2023 |  | 1, 2 | 0
07100007 | Next | Next |  |  | 7/30/2023 | South Raccoon | Next | Phase 1 | 2023/08/31 |  |  | YES |  | FY21_2A | 6/11/2023 | TODO: RAW, DRAFT, Addl | 1, 2 | 0
07100008 | Next | Next |  |  | 12/30/2023 | Lake Red Rock | Next | Phase 1 | 2024/03/24 |  |  | Reina |  | FY21_2A | 11/11/2023 |  | 1, 2 | 0
07100009 | Next | Next |  |  | 8/4/2024 | Lower Des Moines | Next | Phase 1 | 2024/08/04 |  |  | R+E |  | FY21_2A | 7/25/2024 |  | 1, 2 | 0
10230002 | Submitted | In-Progress |  | KTG | 9/9/2024 | Floyd | In-Progress | Pass 1/2 | 2024/07/12 | 2024/09/10 | 2024/09/12 | Erika, Reina |  | FY22_3B | 7/8/2024 | Passed MIP Validation | All on MM | 0
10230003 | In-Progress | In-Progress |  | RK | 8/5/2024 | Little Sioux | In-Progress | Pass 1/2 | 2024/08/07 | 2024/10/15 | 2024/10/15 | E + M |  | FY22_3B | 7/16/2024 | Passed MIP Validation | 1, 2 | 0
10230004 | Submitted | In-Progress |  | MT | 8/1/2024 | Monona-Harrison Ditch | In-Progress | Pass 1/2 | 2024/08/01 | 2024/10/07 | 2024/10/10 | Reina |  | FY22_3B | 3/12/2024 | Passed MIP Validation | 1, 2 | 0
10230005 | Submitted | In-Progress |  | RK | 7/11/2024 | Maple | In-Progress | Pass 1/2 | 2024/06/12 |  |  | Erika |  | FY22_3B | 7/8/2024 | MIP Exception | 1, 2 | 0
10230007 | In-Progress | In-Progress |  | MT | 7/30/2024 | Boyer | In-Progress | Pass 1/2 | 2024/07/30 | 2024/10/15 | 2024/10/15 | Reina |  | FY22_3B | 7/21/2024 | Passed MIP Validation | 1, 2 | 0
07060005 | Approved | Submitted | WSE/Depth; CSLF; PAC; Velocity | EC | 2/28/2024 | Apple-Plum | In Backcheck | Pass 2/2 | 2024/04/04 | 2024/04/05 | 2024/04/05 | Erika |  | FY20_1A | 1/10/2024 | TODO: Missing 0.2% Vel grid | All on MM | 100
07080201 | Approved | Submitted | WSE/Depth; CSLF; PAC; Velocity | RK | 12/30/2023 | Upper Cedar | In Backcheck | Pass 2/2 | 2024/03/15 | 2024/08/15 | 2024/08/19 | Matt |  | FY20_1A | 11/11/2023 | Passed MIP Validation | All on MM | 100
10170204 | Submitted | In-Progress |  |  | 5/29/2024 | Rock | In-Progress | Pass 1/2 | 2024/05/28 | 2024/05/29 | 2024/05/29 | Matt |  | FY22_3B | 2/10/2024 | Passed MIP Validation | All on MM | 0
10230001 | Submitted | In-Progress |  | RK | 8/20/2024 | Blackbird-Soldier | In-Progress | Pass 1/2 | 2024/08/06 | 2024/10/10 | 2024/10/10 | Erika |  | FY22_3B | 8/1/2024 | Passed MIP Validation | 1, 2 | 0
10230006 | Submitted | In-Progress |  | RK | 8/5/2024 | Big Papillion-Mosquito | In-Progress | Pass 1/2 | 2024/08/06 | 2024/10/07 | 2024/10/08 | Reina |  | FY22_3B | 5/12/2024 | Passed MIP Validation | All on MM | 0
10170203 | Submitted | In-Progress |  |  | 3/30/2024 | Lower Big Sioux | In-Progress | Pass 1/2 | 2024/05/24 | 2024/06/26 | 2024/05/24 | Matt |  | FY22_3B | 2/10/2024 | Passed MIP Validation | All on MM | 0
07060003 | Approved | Submitted | WSE/Depth; CSLF; PAC; Velocity | MT | 1/30/2024 | Grant-Little Maquoketa | In Backcheck | Pass 2/2 | 2024/03/15 | 2024/06/26 | 2024/05/22 | Erika |  | FY20_1A | 12/12/2023 | Passed MIP Validation | All on MM | 100
07080101 | Approved | Submitted | WSE/Depth; CSLF; PAC; Velocity | MT | 3/30/2024 | Copperas-Duck | In Backcheck | Pass 2/2 | 2024/04/20 | 2024/04/20 | 2024/05/01 | Reina |  | FY20_1A | 2/10/2024 | Passed MIP Validation | All on MM | 100
07110001 | Next | Next |  |  | 2/28/2024 | Bear-Wyaconda | Next | Phase 1 | 2024/03/26 | 2024/03/26 | 2024/03/26 | Reina |  | FY21_2A | 1/10/2024 |  | All on MM | 0