## Tracking_Main_values
HUC8 | Name | TO Area | Draft | Floodplain | Hydraulics | P01 GDB | RAW Grids | DFIRM Grids | Additional Grids | Missing Grids | Prod Stage | FRP % | Model Complete | P01 Analyst | Notes | Has AECOM Tie | MIP_Case
07060005 | Apple-Plum | FY20_1A | Approved | Approved | Approved | 2024-02-28 | 2024-04-04 | 2024/04/05 | 2024/04/05 | All on MM | Pass 2/2 | 100 | 2024-01-10 | Erika | TODO: Missing 0.2% Vel grid | NO | 21-07-0002S
07080201 | Upper Cedar | FY20_1A | Approved | Approved | Approved | 2023-12-30 | 2024-03-15 | 2024/08/15 | 2024/08/19 | All on MM | Pass 2/2 | 100 | 2023-11-11 | Matt | Passed MIP Validation | YES | 21-07-0002S
07060004 | Turkey | FY20_1A | Approved | Approved | Approved | 2024-05-22 | 2024-04-15 | 2024/08/27 | 2024/05/22 | All on MM | Pass 2/2 | 100 | 2023-11-11 | Multi | Passed MIP Validation | NO | 21-07-0002S
07060006 | Maquoketa | FY20_1A | Approved | Approved | Approved | 2024-05-22 | 2024-05-17 | 2024/05/21 | 2024/05/21 | All on MM | Pass 1/2 | 100 | 2023-12-12 | Multi | Passed MIP Validation; Round 2 Validation 10/11/2024 | NO | 21-07-0002S
07080103 | Lower Wapsipinicon | FY20_1A | Approved | Approved | Approved | 2024-05-22 | 2024-05-09 | 2024/08/14 | 2024/05/22 | All on MM | Pass 1/2 | 100 | 2024-01-10 | Matt | Passed MIP Validation; Round 2 Validation 10/11/2024 | NO | 21-07-0002S
07060002 | Upper Iowa | FY20_1A | Approved | Approved | Approved | 2023-11-30 | 2024-02-23 | 2024/03/10 | 2024/08/20 | All on MM | Pass 1/2 | 100 | 2023-10-12 | Reina | Passed MIP Validation; Round 2 Validation 10/11/2024 | NO | 21-07-0002S
07060003 | Grant-Little Maquoketa | FY20_1A | Approved | Approved | Approved | 2024-01-30 | 2024-03-15 | 2024/06/26 | 2024/05/22 | All on MM | Pass 2/2 | 100 | 2023-12-12 | Erika | Passed MIP Validation | NO | 21-07-0002S
07080206 | Lower Cedar | FY20_1A | Approved | Approved | Approved | 2024-07-13 | 2024-06-14 | 2024/07/16 | 2024/07/18 | All on MM | Pass 1/2 | 100 | 2024-05-31 | Reina | Passed MIP Validation; Round 2 Validation 10/11/2024 | YES | 21-07-0002S
07080101 | Copperas-Duck | FY20_1A | Approved | In Backcheck | Approved | 2024-03-30 | 2024-04-20 | 2024/04/20 | 2024/05/01 | All on MM | Pass 2/2 | 100 | 2024-02-10 | Reina | Passed MIP Validation | YES | 21-07-0002S
07060001 | Coon-Yellow | FY20_1A | Approved | Approved | Approved | 2023-11-30 | 2024-02-23 | 2024/08/20 | 2024/08/20 | All on MM | Pass 2/2 | 100 | 2023-10-12 | Matt | Passed MIP Validation | NO | 21-07-0002S
07080102 | Upper Wapsipinicon | FY20_1A | Approved | Approved | Approved | 2023-12-30 | 2024-04-15 | 2024/08/14 | 2024/05/22 | All on MM | Pass 2/2 | 100 | 2023-11-11 | Matt | Passed MIP Validation | YES | 21-07-0002S
07100008 | Lake Red Rock | FY21_2A | Next | Next | Next | 2023-12-30 | 2024-03-24 |  |  | 1, 2 | Phase 1 | 0 | 2023-11-11 | Reina |  | YES | 22-07-0035S
07100009 | Lower Des Moines | FY21_2A | Next | Next | Next | 2024-08-04 | 2024-08-04 | 2024/11/20 |  | 1, 2 | Phase 1 | 0 | 2024-07-25 | R+E |  | YES | 22-07-0035S
07100006 | North Raccoon | FY21_2A | Next | Next | Next | 2024-02-26 | 2024-02-13 |  |  | 1, 2 | Phase 1 | 0 | 2023-08-12 | YES |  | YES | 22-07-0035S
07100007 | South Raccoon | FY21_2A | Next | Next | Next | 2023-07-30 | 2023-08-31 |  |  | 1, 2 | Phase 1 | 0 | 2023-06-11 | YES | TODO: RAW, DRAFT, Addl | YES | 22-07-0035S
07080105 | South Skunk | FY21_2A | Next | Next | Next | 2024-06-03 | 2024-03-05 | 2024/06/17 |  | 2 | Phase 1 | 0 | 2023-11-11 | Erika |  | YES | 22-07-0035S
07110001 | Bear-Wyaconda | FY21_2A | Next | Next | Next | 2024-02-28 | 2024-03-26 | 2024/03/26 | 2024/03/26 | All on MM | Phase 1 | 0 | 2024-01-10 | Reina |  | YES | 22-07-0035S
10170203 | Lower Big Sioux | FY22_3B | Submitted | Submitted | In Backcheck | 2024-03-30 | 2024-05-24 | 2024/06/26 | 2024/05/24 | All on MM | Pass 1/2 | 100 | 2024-02-10 | Matt | All Hydraulics Spatial Files uploaded 10/16 | NO | 23-07-0036S
10230007 | Boyer | FY22_3B | Submitted | Submitted | Submitted | 2024-07-30 | 2024-07-30 | 2024/10/15 | 2024/10/15 | All on MM | Pass 1/2 | 100 | 2024-07-21 | Reina | All Hydraulics Spatial Files uploaded 10/16 | YES | 23-07-0037S
10230005 | Maple | FY22_3B | Approved | Submitted | Submitted | 2024-07-11 | 2024-06-12 | 2024/10/16 | 2024/10/16 | All on MM | Pass 1/2 | 100 | 2024-07-08 | Erika | MIP Exception; All Hydraulics Spatial Files uploaded 10/16 | NO | 23-07-0037S
10230002 | Floyd | FY22_3B | Approved | Submitted | Submitted | 2024-09-09 | 2024-07-12 | 2024/09/10 | 2024/09/12 | All on MM | Pass 1/2 | 100 | 2024-07-08 | Erika, Reina | All Hydraulics Spatial Files uploaded 10/16 | NO | 23-07-0037S
10230004 | Monona-Harrison Ditch | FY22_3B | Approved | Submitted | Submitted | 2024-08-01 | 2024-08-01 | 2024/10/07 | 2024/10/10 | All on MM | Pass 1/2 | 100 | 2024-03-12 | Reina | All Hydraulics Spatial Files uploaded 10/16 | NO | 23-07-0037S
10170204 | Rock | FY22_3B | Submitted | Submitted | In Backcheck | 2024-05-29 | 2024-05-28 | 2024/05/29 | 2024/05/29 | All on MM | Pass 1/2 | 100 | 2024-02-10 | Matt | All Hydraulics Spatial Files uploaded 10/16 | NO | 23-07-0036S
10230006 | Big Papillion-Mosquito | FY22_3B | Submitted | Submitted | Submitted | 2024-08-05 | 2024-08-06 | 2024/10/07 | 2024/10/08 | All on MM | Pass 1/2 | 100 | 2024-05-12 | Reina | All Hydraulics Spatial Files uploaded 10/16 | YES | 23-07-0037S
10230003 | Little Sioux | FY22_3B | Submitted | Submitted | Submitted | 2024-08-05 | 2024-08-07 | 2024/10/15 | 2024/10/15 | All on MM | Pass 1/2 | 100 | 2024-07-16 | E + M | All Hydraulics Spatial Files uploaded 10/16 | YES | 23-07-0037S
10230001 | Blackbird-Soldier | FY22_3B | Submitted | Submitted | Submitted | 2024-08-20 | 2024-08-06 | 2024/10/10 | 2024/10/10 | All on MM | Pass 1/2 | 100 | 2024-08-01 | Erika | All Hydraulics Spatial Files uploaded 10/16 | NO | 23-07-0037S

## Tracking_Main
HUC8 | Name | TO Area | Draft | Floodplain | Hydraulics | P01 GDB | RAW Grids | DFIRM Grids | Additional Grids | Missing Grids | Prod Stage | FRP % | Model Complete | P01 Analyst | Notes | Has AECOM Tie | MIP_Case
07060005 | Apple-Plum | FY20_1A | Approved | Approved | Approved | 2024-02-28 | 2024-04-04 | 2024/04/05 | 2024/04/05 | All on MM | Pass 2/2 | 100 | 2024-01-10 | Erika | TODO: Missing 0.2% Vel grid | NO | 21-07-0002S
07080201 | Upper Cedar | FY20_1A | Approved | Approved | Approved | 2023-12-30 | 2024-03-15 | 2024/08/15 | 2024/08/19 | All on MM | Pass 2/2 | 100 | 2023-11-11 | Matt | Passed MIP Validation | YES | 21-07-0002S
07060004 | Turkey | FY20_1A | Approved | Approved | Approved | 2024-05-22 | 2024-04-15 | 2024/08/27 | 2024/05/22 | All on MM | Pass 2/2 | 100 | 2023-11-11 | Multi | Passed MIP Validation | NO | 21-07-0002S
07060006 | Maquoketa | FY20_1A | Approved | Approved | Approved | 2024-05-22 | 2024-05-17 | 2024/05/21 | 2024/05/21 | All on MM | Pass 1/2 | 100 | 2023-12-12 | Multi | Passed MIP Validation; Round 2 Validation 10/11/2024 | NO | 21-07-0002S
07080103 | Lower Wapsipinicon | FY20_1A | Approved | Approved | Approved | 2024-05-22 | 2024-05-09 | 2024/08/14 | 2024/05/22 | All on MM | Pass 1/2 | 100 | 2024-01-10 | Matt | Passed MIP Validation; Round 2 Validation 10/11/2024 | NO | 21-07-0002S
07060002 | Upper Iowa | FY20_1A | Approved | Approved | Approved | 2023-11-30 | 2024-02-23 | 2024/03/10 | 2024/08/20 | All on MM | Pass 1/2 | 100 | 2023-10-12 | Reina | Passed MIP Validation; Round 2 Validation 10/11/2024 | NO | 21-07-0002S
07060003 | Grant-Little Maquoketa | FY20_1A | Approved | Approved | Approved | 2024-01-30 | 2024-03-15 | 2024/06/26 | 2024/05/22 | All on MM | Pass 2/2 | 100 | 2023-12-12 | Erika | Passed MIP Validation | NO | 21-07-0002S
07080206 | Lower Cedar | FY20_1A | Approved | Approved | Approved | 2024-07-13 | 2024-06-14 | 2024/07/16 | 2024/07/18 | All on MM | Pass 1/2 | 100 | 2024-05-31 | Reina | Passed MIP Validation; Round 2 Validation 10/11/2024 | YES | 21-07-0002S
07080101 | Copperas-Duck | FY20_1A | Approved | In Backcheck | Approved | 2024-03-30 | 2024-04-20 | 2024/04/20 | 2024/05/01 | All on MM | Pass 2/2 | 100 | 2024-02-10 | Reina | Passed MIP Validation | YES | 21-07-0002S
07060001 | Coon-Yellow | FY20_1A | Approved | Approved | Approved | 2023-11-30 | 2024-02-23 | 2024/08/20 | 2024/08/20 | All on MM | Pass 2/2 | 100 | 2023-10-12 | Matt | Passed MIP Validation | NO | 21-07-0002S
07080102 | Upper Wapsipinicon | FY20_1A | Approved | Approved | Approved | 2023-12-30 | 2024-04-15 | 2024/08/14 | 2024/05/22 | All on MM | Pass 2/2 | 100 | 2023-11-11 | Matt | Passed MIP Validation | YES | 21-07-0002S
07100008 | Lake Red Rock | FY21_2A | Next | Next | Next | 2023-12-30 | 2024-03-24 |  |  | 1, 2 | Phase 1 | 0 | 2023-11-11 | Reina |  | YES | 22-07-0035S
07100009 | Lower Des Moines | FY21_2A | Next | Next | Next | 2024-08-04 | 2024-08-04 | 2024/11/20 |  | 1, 2 | Phase 1 | 0 | 2024-07-25 | R+E |  | YES | 22-07-0035S
07100006 | North Raccoon | FY21_2A | Next | Next | Next | 2024-02-26 | 2024-02-13 |  |  | 1, 2 | Phase 1 | 0 | 2023-08-12 | YES |  | YES | 22-07-0035S
07100007 | South Raccoon | FY21_2A | Next | Next | Next | 2023-07-30 | 2023-08-31 |  |  | 1, 2 | Phase 1 | 0 | 2023-06-11 | YES | TODO: RAW, DRAFT, Addl | YES | 22-07-0035S
07080105 | South Skunk | FY21_2A | Next | Next | Next | 2024-06-03 | 2024-03-05 | 2024/06/17 |  | 2 | Phase 1 | 0 | 2023-11-11 | Erika |  | YES | 22-07-0035S
07110001 | Bear-Wyaconda | FY21_2A | Next | Next | Next | 2024-02-28 | 2024-03-26 | 2024/03/26 | 2024/03/26 | All on MM | Phase 1 | 0 | 2024-01-10 | Reina |  | YES | 22-07-0035S
10170203 | Lower Big Sioux | FY22_3B | Submitted | Submitted | In Backcheck | 2024-03-30 | 2024-05-24 | 2024/06/26 | 2024/05/24 | All on MM | Pass 1/2 | 100 | 2024-02-10 | Matt | All Hydraulics Spatial Files uploaded 10/16 | NO | 23-07-0036S
10230007 | Boyer | FY22_3B | Submitted | Submitted | Submitted | 2024-07-30 | 2024-07-30 | 2024/10/15 | 2024/10/15 | All on MM | Pass 1/2 | 100 | 2024-07-21 | Reina | All Hydraulics Spatial Files uploaded 10/16 | YES | 23-07-0037S
10230005 | Maple | FY22_3B | Approved | Submitted | Submitted | 2024-07-11 | 2024-06-12 | 2024/10/16 | 2024/10/16 | All on MM | Pass 1/2 | 100 | 2024-07-08 | Erika | MIP Exception; All Hydraulics Spatial Files uploaded 10/16 | NO | 23-07-0037S
10230002 | Floyd | FY22_3B | Approved | Submitted | Submitted | 2024-09-09 | 2024-07-12 | 2024/09/10 | 2024/09/12 | All on MM | Pass 1/2 | 100 | 2024-07-08 | Erika, Reina | All Hydraulics Spatial Files uploaded 10/16 | NO | 23-07-0037S
10230004 | Monona-Harrison Ditch | FY22_3B | Approved | Submitted | Submitted | 2024-08-01 | 2024-08-01 | 2024/10/07 | 2024/10/10 | All on MM | Pass 1/2 | 100 | 2024-03-12 | Reina | All Hydraulics Spatial Files uploaded 10/16 | NO | 23-07-0037S
10170204 | Rock | FY22_3B | Submitted | Submitted | In Backcheck | 2024-05-29 | 2024-05-28 | 2024/05/29 | 2024/05/29 | All on MM | Pass 1/2 | 100 | 2024-02-10 | Matt | All Hydraulics Spatial Files uploaded 10/16 | NO | 23-07-0036S
10230006 | Big Papillion-Mosquito | FY22_3B | Submitted | Submitted | Submitted | 2024-08-05 | 2024-08-06 | 2024/10/07 | 2024/10/08 | All on MM | Pass 1/2 | 100 | 2024-05-12 | Reina | All Hydraulics Spatial Files uploaded 10/16 | YES | 23-07-0037S
10230003 | Little Sioux | FY22_3B | Submitted | Submitted | Submitted | 2024-08-05 | 2024-08-07 | 2024/10/15 | 2024/10/15 | All on MM | Pass 1/2 | 100 | 2024-07-16 | E + M | All Hydraulics Spatial Files uploaded 10/16 | YES | 23-07-0037S
10230001 | Blackbird-Soldier | FY22_3B | Submitted | Submitted | Submitted | 2024-08-20 | 2024-08-06 | 2024/10/10 | 2024/10/10 | All on MM | Pass 1/2 | 100 | 2024-08-01 | Erika | All Hydraulics Spatial Files uploaded 10/16 | NO | 23-07-0037S