## Tracking_Main
Stages Complete | HUC8 | Name | FRP % | FRP Complete | BFE_TODO | PBL_Assign | P01_MM | RAW_Grd_MM | DFIRM_Grd_MM | Addl_Grd_MM | Prod Stage | P01 Analyst | AECOM Tie-in | TO_Area | Model Complete | Notes | Unfinished Grids
| 07060001 | Coon-Yellow |  |  | F | QB
| 07060002 | Upper Iowa |  |  | F | MB
| 07060004 | Turkey |  |  | F | EC
| 07060006 | Maquoketa |  |  | F | RK
| 07080102 | Upper Wapsipinicon |  |  | F | KTG
| 07080103 | Lower Wapsipinicon |  |  | F | MT
| 07080105 | South Skunk |  |  | T
| 07080206 | Lower Cedar |  |  | F | QB
| 07100006 | North Raccoon |  |  | T
| 07100007 | South Raccoon |  |  | T
| 07100008 | Lake Red Rock |  |  | T
| 07100009 | Lower Des Moines |  |  | T
| 10230002 | Floyd |  |  | T
| 10230003 | Little Sioux |  |  | T | RK
| 10230004 | Monona-Harrison Ditch |  |  | T
| 10230005 | Maple |  |  | T
| 10230007 | Boyer |  |  | T
| 07060005 | Apple-Plum |  |  | F | EC
| 07080201 | Upper Cedar |  |  | F | RK
| 10170204 | Rock |  |  | T
| 10230001 | Blackbird-Soldier |  |  | T
| 10230006 | Big Papillion-Mosquito |  |  | T
| 10170203 | Lower Big Sioux |  |  | T
| 07060003 | Grant-Little Maquoketa |  |  | F | MT
| 07080101 | Copperas-Duck |  |  | F | MT
| 07110001 | Bear-Wyaconda |  |  | T

## Progress_Domains
Prod Stage | Number
Pass 2/2 | 7
Pass 1/2 | 6
DD Submit | 5
DD Internal | 4
DD Mapping | 3
Phase 1 | 2
Mapping In-Progress | 1

## Tracking_Main_values
HUC8 | P02a_Assign | P01_MM | Name | RAW_Grd_MM | DFIRM_Grd_MM | Addl_Grd_MM | Prod Stage | P01 Analyst | AECOM Tie-in | TO_Area | Model Complete | Notes | which_grid | Addl_Gri_1 | BFE_TODO_F | Contract_1 | DFIRM_Gr_1 | Final_Mo_1 | FRP_First | Grids_No_1 | huc8_First | Mapping__1 | name_First | PBL_Assi_1 | Phase_1__1 | Producti_1 | RAW_Grid_F | TO_Area_Fi | which_gr_1
07060001 | QB | 11/30/2023 | Coon-Yellow | 2024/02/23 | 2024/08/20 | 2024/08/20 | Pass 2/2 | Matt |  | FY20_1A | 10/12/2023 | Passed MIP Validation | All on MM | 2024/08/20 | F |  | 2024/08/20 | 2023/10/12 | CSLF; PAC; Velocity | Passed MIP Validation | 07060001 | Matt | Coon-Yellow | QB | 2023/11/30 | Pass 2/2 | 2024/02/23 | FY20_1A | All on MM
07060002 | MB | 11/30/2023 | Upper Iowa | 2024/02/23 | 2024/03/10 | 2024/08/20 | Pass 1/2 | Reina |  | FY20_1A | 10/12/2023 | Passed MIP Validation | All on MM | 2024/08/20 | F |  | 2024/03/10 | 2023/10/12 | CSLF; PAC; Velocity | Passed MIP Validation | 07060002 | Reina | Upper Iowa | MB | 2023/11/30 | Pass 1/2 | 2024/02/23 | FY20_1A | All on MM
07060004 | EC | 5/22/2024 | Turkey | 2024/04/15 | 2024/08/27 | 2024/05/22 | Pass 2/2 | Multi |  | FY20_1A | 11/11/2023 | Passed MIP Validation | All on MM | 2024/05/22 | F |  | 2024/08/27 | 2023/11/11 | CSLF; PAC; Velocity | Passed MIP Validation | 07060004 | Multi | Turkey | EC | 2024/05/22 | Pass 2/2 | 2024/04/15 | FY20_1A | All on MM
07060006 | RK | 5/22/2024 | Maquoketa | 2024/05/17 | 2024/05/21 | 2024/05/21 | Pass 1/2 | Multi |  | FY20_1A | 12/12/2023 | Passed MIP Validation | All on MM | 2024/05/21 | F |  | 2024/05/21 | 2023/12/12 | CSLF; PAC; Velocity | Passed MIP Validation | 07060006 | Multi | Maquoketa | RK | 2024/05/22 | Pass 1/2 | 2024/05/17 | FY20_1A | All on MM
07080102 | KTG | 12/30/2023 | Upper Wapsipinicon | 2024/04/15 | 2024/08/14 | 2024/05/22 | Pass 2/2 | Matt |  | FY20_1A | 11/11/2023 | Passed MIP Validation | All on MM | 2024/05/22 | F |  | 2024/08/14 | 2023/11/11 | CSLF; PAC; Velocity | Passed MIP Validation | 07080102 | Matt | Upper Wapsipinicon | KTG | 2023/12/30 | Pass 2/2 | 2024/04/15 | FY20_1A | All on MM
07080103 | MT | 5/22/2024 | Lower Wapsipinicon | 2024/05/09 | 2024/08/14 | 2024/05/22 | Pass 1/2 | Matt |  | FY20_1A | 1/10/2024 | Passed MIP Validation | All on MM | 2024/05/22 | F |  | 2024/08/14 | 2024/01/10 | CSLF; PAC; Velocity | Passed MIP Validation | 07080103 | Matt | Lower Wapsipinicon | MT | 2024/05/22 | Pass 1/2 | 2024/05/09 | FY20_1A | All on MM
07080105 |  | 6/3/2024 | South Skunk | 2024/03/05 | 2024/06/17 |  | Phase 1 | Erika |  | FY21_2A | 11/11/2023 |  | 2 |  | T |  | 2024/06/17 | 2023/11/11 |  |  | 07080105 | Erika | South Skunk |  | 2024/06/03 | Phase 1 | 2024/03/05 | FY21_2A | 2
07080206 | QB | 7/13/2024 | Lower Cedar | 2024/06/14 | 2024/07/16 | 2024/07/18 | Pass 1/2 | Reina |  | FY20_1A | 5/31/2024 | Passed MIP Validation | All on MM | 2024/07/18 | F |  | 2024/07/16 | 2024/05/31 | CSLF; PAC; Velocity | Passed MIP Validation | 07080206 | Reina | Lower Cedar | QB | 2024/07/13 | Pass 1/2 | 2024/06/14 | FY20_1A | All on MM
07100006 |  | 2/26/2024 | North Raccoon | 2024/02/13 |  |  | Phase 1 | YES |  | FY21_2A | 8/12/2023 |  | 1, 2 |  | T |  |  | 2023/08/12 |  |  | 07100006 | YES | North Raccoon |  | 2024/02/26 | Phase 1 | 2024/02/13 | FY21_2A | 1, 2
07100007 |  | 7/30/2023 | South Raccoon | 2023/08/31 |  |  | Phase 1 | YES |  | FY21_2A | 6/11/2023 | TODO: RAW, DRAFT, Addl | 1, 2 |  | T |  |  | 2023/06/11 |  | TODO: RAW, DRAFT, Addl | 07100007 | YES | South Raccoon |  | 2023/07/30 | Phase 1 | 2023/08/31 | FY21_2A | 1, 2
07100008 |  | 12/30/2023 | Lake Red Rock | 2024/03/24 |  |  | Phase 1 | Reina |  | FY21_2A | 11/11/2023 |  | 1, 2 |  | T |  |  | 2023/11/11 |  |  | 07100008 | Reina | Lake Red Rock |  | 2023/12/30 | Phase 1 | 2024/03/24 | FY21_2A | 1, 2
07100009 |  | 8/4/2024 | Lower Des Moines | 2024/08/04 |  |  | Phase 1 | R+E |  | FY21_2A | 7/25/2024 |  | 1, 2 |  | T |  |  | 2024/07/25 |  |  | 07100009 | R+E | Lower Des Moines |  | 2024/08/04 | Phase 1 | 2024/08/04 | FY21_2A | 1, 2
10230002 | KTG | 9/9/2024 | Floyd | 2024/07/12 | 2024/09/10 | 2024/09/12 | Pass 1/2 | Erika, Reina |  | FY22_3B | 7/8/2024 | Passed MIP Validation | All on MM | 2024/09/12 | F |  | 2024/09/10 | 2024/07/08 |  | Passed MIP Validation | 10230002 | Erika, Reina | Floyd | KTG | 2024/09/09 | Pass 1/2 | 2024/07/12 | FY22_3B | All on MM
10230003 | RK | 8/5/2024 | Little Sioux | 2024/08/07 |  |  | DD Mapping | E + M |  | FY22_3B | 7/16/2024 | TODO: PBL, BFE, Validation | 1, 2 |  | F |  |  | 2024/07/16 |  | TODO: PBL, BFE, Validation | 10230003 | E + M | Little Sioux | RK | 2024/08/05 | DD Mapping | 2024/08/07 | FY22_3B | 1, 2
10230004 | MT | 8/1/2024 | Monona-Harrison Ditch | 2024/08/01 | 2024/10/07 | 2024/10/10 | Pass 1/2 | Reina |  | FY22_3B | 3/12/2024 | MIP Validation Passed | 1, 2 | 2024/10/10 | F |  | 2024/10/07 | 2024/03/12 |  | MIP Validation Passed | 10230004 | Reina | Monona-Harrison Ditch | MT | 2024/08/01 | Pass 1/2 | 2024/08/01 | FY22_3B | 1, 2
10230005 | RK | 7/11/2024 | Maple | 2024/06/12 |  |  | Pass 1/2 | Erika |  | FY22_3B | 7/8/2024 | MIP Exception | 1, 2 |  | F |  |  | 2024/07/08 |  | MIP Exception | 10230005 | Erika | Maple | RK | 2024/07/11 | Pass 1/2 | 2024/06/12 | FY22_3B | 1, 2
10230007 | MT | 7/30/2024 | Boyer | 2024/07/30 |  |  | DD Mapping | Reina |  | FY22_3B | 7/21/2024 | TODO: PBL, BFE, Validation | 1, 2 |  | F |  |  | 2024/07/21 |  | TODO: PBL, BFE, Validation | 10230007 | Reina | Boyer | MT | 2024/07/30 | DD Mapping | 2024/07/30 | FY22_3B | 1, 2
07060005 | EC | 2/28/2024 | Apple-Plum | 2024/04/04 | 2024/04/05 | 2024/04/05 | Pass 2/2 | Erika |  | FY20_1A | 1/10/2024 | TODO: Missing 0.2% Vel grid | All on MM | 2024/04/05 | F |  | 2024/04/05 | 2024/01/10 | CSLF; PAC; Velocity | TODO: Missing 0.2% Vel grid | 07060005 | Erika | Apple-Plum | EC | 2024/02/28 | Pass 2/2 | 2024/04/04 | FY20_1A | All on MM
07080201 | RK | 12/30/2023 | Upper Cedar | 2024/03/15 | 2024/08/15 | 2024/08/19 | Pass 2/2 | Matt |  | FY20_1A | 11/11/2023 | Passed MIP Validation | All on MM | 2024/08/19 | F |  | 2024/08/15 | 2023/11/11 | CSLF; PAC; Velocity | Passed MIP Validation | 07080201 | Matt | Upper Cedar | RK | 2023/12/30 | Pass 2/2 | 2024/03/15 | FY20_1A | All on MM
10170204 |  | 5/29/2024 | Rock | 2024/05/28 | 2024/05/29 | 2024/05/29 | Pass 1/2 | Matt |  | FY22_3B | 2/10/2024 | Passed MIP Validation | All on MM | 2024/05/29 | F |  | 2024/05/29 | 2024/02/10 |  | Passed MIP Validation | 10170204 | Matt | Rock |  | 2024/05/29 | Pass 1/2 | 2024/05/28 | FY22_3B | All on MM
10230001 | RK | 8/20/2024 | Blackbird-Soldier | 2024/08/06 | 2024/10/10 | 2024/10/10 | Pass 1/2 | Erika |  | FY22_3B | 8/1/2024 | Passed MIP Validation | 1, 2 | 2024/10/10 | F |  | 2024/10/10 | 2024/08/01 |  | Passed MIP Validation | 10230001 | Erika | Blackbird-Soldier | RK | 2024/08/20 | Pass 1/2 | 2024/08/06 | FY22_3B | 1, 2
10230006 | RK | 8/5/2024 | Big Papillion-Mosquito | 2024/08/06 | 2024/10/07 | 2024/10/08 | Pass 1/2 | Reina |  | FY22_3B | 5/12/2024 | Passed MIP Validation | All on MM | 2024/10/08 | F |  | 2024/10/07 | 2024/05/12 |  | Passed MIP Validation | 10230006 | Reina | Big Papillion-Mosquito | RK | 2024/08/05 | Pass 1/2 | 2024/08/06 | FY22_3B | All on MM
10170203 |  | 3/30/2024 | Lower Big Sioux | 2024/05/24 | 2024/06/26 | 2024/05/24 | Pass 1/2 | Matt |  | FY22_3B | 2/10/2024 | Passed MIP Validation | All on MM | 2024/05/24 | F |  | 2024/06/26 | 2024/02/10 |  | Passed MIP Validation | 10170203 | Matt | Lower Big Sioux |  | 2024/03/30 | Pass 1/2 | 2024/05/24 | FY22_3B | All on MM
07060003 | MT | 1/30/2024 | Grant-Little Maquoketa | 2024/03/15 | 2024/06/26 | 2024/05/22 | Pass 2/2 | Erika |  | FY20_1A | 12/12/2023 | Passed MIP Validation | All on MM | 2024/05/22 | F |  | 2024/06/26 | 2023/12/12 | CSLF; PAC; Velocity | Passed MIP Validation | 07060003 | Erika | Grant-Little Maquoketa | MT | 2024/01/30 | Pass 2/2 | 2024/03/15 | FY20_1A | All on MM
07080101 | MT | 3/30/2024 | Copperas-Duck | 2024/04/20 | 2024/04/20 | 2024/05/01 | Pass 2/2 | Reina |  | FY20_1A | 2/10/2024 | Passed MIP Validation | All on MM | 2024/05/01 | F |  | 2024/04/20 | 2024/02/10 | CSLF; PAC; Velocity | Passed MIP Validation | 07080101 | Reina | Copperas-Duck | MT | 2024/03/30 | Pass 2/2 | 2024/04/20 | FY20_1A | All on MM
07110001 |  | 2/28/2024 | Bear-Wyaconda | 2024/03/26 | 2024/03/26 | 2026/03/28 | Phase 1 | Reina |  | FY21_2A | 1/10/2024 |  | All on MM | 2026/03/28 | T |  | 2024/03/26 | 2024/01/10 |  |  | 07110001 | Reina | Bear-Wyaconda |  | 2024/02/28 | Phase 1 | 2024/03/26 | FY21_2A | All on MM