## Tracking_Main
Stages Complete | HUC8 | Unfinished Grids | Name | BFE_TODO | PBL_Assign | P01_MM | RAW_Grd_MM | DFIRM_Grd_MM | Addl_Grd_MM | Prod Stage | P01 Analyst | AECOM Tie-in | TO_Area | Model Complete | Notes
| 07060001 | All on MM | Coon-Yellow | F | QB | 2023/11/30 | 2024/02/23 | 2024/08/20 | 2024/08/20 | Pass 1/2 | Matt | NO | FY20_1A | 2023/10/12 | Passed MIP Validation
| 07060002 | All on MM | Upper Iowa | F | MB | 2023/11/30 | 2024/02/23 | 2024/03/10 | 2024/08/20 | DD Submit | Reina | NO | FY20_1A | 2023/10/12 | TODO: PBL, Validation
| 07060004 | All on MM | Turkey | F | EC | 2024/05/22 | 2024/04/15 | 2024/08/27 | 2024/05/22 | DD Submit | Multi | NO | FY20_1A | 2023/11/11 | TODO: Validation; UPDATE: 1% PLUS
| 07060006 | All on MM | Maquoketa | F | RK | 2024/05/22 | 2024/05/17 | 2024/05/21 | 2024/05/21 | DD Internal | Multi | NO | FY20_1A | 2023/12/12 | TODO: Validation
| 07080102 | All on MM | Upper Wapsipinicon | F | KTG | 2023/12/30 | 2024/04/15 | 2024/08/14 | 2024/05/22 | DD Submit | Matt | YES | FY20_1A | 2023/11/11 | UPDATE: DFIRM Clipped
| 07080103 | All on MM | Lower Wapsipinicon | F | MT | 2024/05/22 | 2024/05/09 | 2024/08/14 | 2024/05/22 | DD Submit | Matt | NO | FY20_1A | 2024/01/10 | TODO: Validation; UPDATE: DFIRM grid extents
| 07080105 | 2 | South Skunk | T |  | 2024/06/03 | 2024/03/05 | 2024/06/17 | 0000/00/00 | Phase 1 | Erika | YES | FY21_2A | 2023/11/11
| 07080206 | All on MM | Lower Cedar | F | QB | 2024/07/13 | 2024/06/14 | 2024/07/16 | 2024/07/18 | DD Submit | Reina | YES | FY20_1A | 2024/05/31 | TODO: Validation
| 07100006 | 1, 2 | North Raccoon | T |  | 2024/02/26 | 2024/02/13 | 0000/00/00 | 0000/00/00 | Phase 1 | YES | YES | FY21_2A | 2023/08/12
| 07100007 | 1, 2 | South Raccoon | T |  | 2023/07/30 | 2023/08/31 | 0000/00/00 | 0000/00/00 | Phase 1 | YES | YES | FY21_2A | 2023/06/11 | TODO: RAW, DRAFT, Addl
| 07100008 | 1, 2 | Lake Red Rock | T |  | 2023/12/30 | 2024/03/24 | 0000/00/00 | 0000/00/00 | Phase 1 | Reina | YES | FY21_2A | 2023/11/11
| 07100009 | 1, 2 | Lower Des Moines | T |  | 2024/08/04 | 2024/08/04 | 0000/00/00 | 0000/00/00 | Phase 1 | R+E | YES | FY21_2A | 2024/07/25
| 10230002 | 1, 2 | Floyd | T |  | 2024/07/10 | 2024/07/12 | 0000/00/00 | 0000/00/00 | Phase 1 | Reina | NO | FY22_3B | 2024/07/08 | TODO: Missing Zone A; PBL, BFE, Validation
| 10230003 | 1, 2 | Little Sioux | T |  | 2024/08/05 | 2024/08/07 | 0000/00/00 | 0000/00/00 | Phase 1 | E + M | YES | FY22_3B | 2024/07/16 | TODO: PBL, BFE, Validation
| 10230004 | 1, 2 | Monona-Harrison Ditch | T |  | 2024/08/01 | 2024/08/01 | 0000/00/00 | 0000/00/00 | Phase 1 | Reina | NO | FY22_3B | 2024/03/12 | TODO: PBL, BFE, Validation
| 10230005 | 1, 2 | Maple | T |  | 2024/07/11 | 2024/06/12 | 0000/00/00 | 0000/00/00 | Phase 1 | Erika | NO | FY22_3B | 2024/07/08 | TODO: PBL, BFE, Validation
| 10230007 | 1, 2 | Boyer | T |  | 2024/07/30 | 2024/07/30 | 0000/00/00 | 0000/00/00 | Phase 1 | Reina | YES | FY22_3B | 2024/07/21 | TODO: PBL, BFE, Validation
| 07060005 | All on MM | Apple-Plum | F | EC | 2024/02/28 | 2024/04/04 | 2024/04/05 | 2024/04/05 | Pass 1/2 | Erika | NO | FY20_1A | 2024/01/10 | Passed MIP Validation
| 07080201 | All on MM | Upper Cedar | F | RK | 2023/12/30 | 2024/03/15 | 2024/08/15 | 2024/08/19 | Pass 1/2 | Matt | YES | FY20_1A | 2023/11/11 | Passed MIP Validation
| 10170204 | All on MM | Rock | T |  | 2024/05/29 | 2024/05/28 | 2024/05/29 | 2024/05/29 | DD Internal | Matt | NO | FY22_3B | 2024/02/10 | TODO: Validation
| 10230001 | 1, 2 | Blackbird-Soldier | T |  | 2024/08/20 | 2024/08/06 | 0000/00/00 | 0000/00/00 | Phase 1 | Erika | NO | FY22_3B | 2024/08/01 | TODO: PBL, BFE, Validation
| 10230006 | 1, 2 | Big Papillion-Mosquito | T |  | 2024/08/05 | 2024/08/06 | 0000/00/00 | 0000/00/00 | Phase 1 | Reina | YES | FY22_3B | 2024/05/12 | TODO: PBL, BFE, Validation
| 10170203 | All on MM | Lower Big Sioux | T |  | 2024/03/30 | 2024/05/24 | 2024/06/26 | 2024/05/24 | DD Internal | Matt | NO | FY22_3B | 2024/02/10 | TODO: Validation
| 07060003 | All on MM | Grant-Little Maquoketa | F | MT | 2024/01/30 | 2024/03/15 | 2024/06/26 | 2024/05/22 | Pass 1/2 | Erika | NO | FY20_1A | 2023/12/12 | Passed MIP Validation
| 07080101 | All on MM | Copperas-Duck | F | MT | 2024/03/30 | 2024/04/20 | 2024/04/20 | 2024/05/01 | DD Internal | Reina | YES | FY20_1A | 2024/02/10 | TODO: Validation
| 07110001 | All on MM | Bear-Wyaconda | T |  | 2024/02/28 | 2024/03/26 | 2024/03/26 | 2026/03/28 | Phase 1 | Reina | YES | FY21_2A | 2024/01/10

## Progress_Domains
Prod Stage | Number
Pass 2/2 | 7
Pass 1/2 | 6
DD Submit | 5
DD Internal | 4
DD Mapping | 3
Phase 1 | 2

## Tracking_Main_values
07060001 | All on MM | Coon-Yellow | F | QB | 2023/11/30 | 2024/02/23 | 2024/08/20 | 2024/08/20 | Pass 1/2 | Matt | NO | FY20_1A | 2023/10/12 | Passed MIP Validation
07060002 | All on MM | Upper Iowa | F | MB | 2023/11/30 | 2024/02/23 | 2024/03/10 | 2024/08/20 | Pass 1/2 | Reina | NO | FY20_1A | 2023/10/12 | Passed MIP Validation
07060004 | All on MM | Turkey | F | EC | 2024/05/22 | 2024/04/15 | 2024/08/27 | 2024/05/22 | Pass 1/2 | Multi | NO | FY20_1A | 2023/11/11 | Passed MIP Validation
07060006 | All on MM | Maquoketa | F | RK | 2024/05/22 | 2024/05/17 | 2024/05/21 | 2024/05/21 | DD Internal | Multi | NO | FY20_1A | 2023/12/12 | TODO: Validation
07080102 | All on MM | Upper Wapsipinicon | F | KTG | 2023/12/30 | 2024/04/15 | 2024/08/14 | 2024/05/22 | DD Submit | Matt | YES | FY20_1A | 2023/11/11 | UPDATE: DFIRM Clipped
07080103 | All on MM | Lower Wapsipinicon | F | MT | 2024/05/22 | 2024/05/09 | 2024/08/14 | 2024/05/22 | DD Submit | Matt | NO | FY20_1A | 2024/01/10 | TODO: Validation; UPDATE: DFIRM grid extents
07080105 | 2 | South Skunk | T |  | 2024/06/03 | 2024/03/05 | 2024/06/17 | 0000/00/00 | Phase 1 | Erika | YES | FY21_2A | 2023/11/11
07080206 | All on MM | Lower Cedar | F | QB | 2024/07/13 | 2024/06/14 | 2024/07/16 | 2024/07/18 | DD Submit | Reina | YES | FY20_1A | 2024/05/31 | TODO: Validation
07100006 | 1, 2 | North Raccoon | T |  | 2024/02/26 | 2024/02/13 | 0000/00/00 | 0000/00/00 | Phase 1 | YES | YES | FY21_2A | 2023/08/12
07100007 | 1, 2 | South Raccoon | T |  | 2023/07/30 | 2023/08/31 | 0000/00/00 | 0000/00/00 | Phase 1 | YES | YES | FY21_2A | 2023/06/11 | TODO: RAW, DRAFT, Addl
07100008 | 1, 2 | Lake Red Rock | T |  | 2023/12/30 | 2024/03/24 | 0000/00/00 | 0000/00/00 | Phase 1 | Reina | YES | FY21_2A | 2023/11/11
07100009 | 1, 2 | Lower Des Moines | T |  | 2024/08/04 | 2024/08/04 | 0000/00/00 | 0000/00/00 | Phase 1 | R+E | YES | FY21_2A | 2024/07/25
10230002 | 1, 2 | Floyd | T |  | 2024/07/10 | 2024/07/12 | 0000/00/00 | 0000/00/00 | Phase 1 | Reina | NO | FY22_3B | 2024/07/08 | TODO: Missing Zone A; PBL, BFE, Validation
10230003 | 1, 2 | Little Sioux | T |  | 2024/08/05 | 2024/08/07 | 0000/00/00 | 0000/00/00 | Phase 1 | E + M | YES | FY22_3B | 2024/07/16 | TODO: PBL, BFE, Validation
10230004 | 1, 2 | Monona-Harrison Ditch | T |  | 2024/08/01 | 2024/08/01 | 0000/00/00 | 0000/00/00 | Phase 1 | Reina | NO | FY22_3B | 2024/03/12 | TODO: PBL, BFE, Validation
10230005 | 1, 2 | Maple | T |  | 2024/07/11 | 2024/06/12 | 0000/00/00 | 0000/00/00 | Phase 1 | Erika | NO | FY22_3B | 2024/07/08 | TODO: PBL, BFE, Validation
10230007 | 1, 2 | Boyer | T |  | 2024/07/30 | 2024/07/30 | 0000/00/00 | 0000/00/00 | Phase 1 | Reina | YES | FY22_3B | 2024/07/21 | TODO: PBL, BFE, Validation
07060005 | All on MM | Apple-Plum | F | EC | 2024/02/28 | 2024/04/04 | 2024/04/05 | 2024/04/05 | Pass 1/2 | Erika | NO | FY20_1A | 2024/01/10 | Passed MIP Validation
07080201 | All on MM | Upper Cedar | F | RK | 2023/12/30 | 2024/03/15 | 2024/08/15 | 2024/08/19 | Pass 1/2 | Matt | YES | FY20_1A | 2023/11/11 | Passed MIP Validation
10170204 | All on MM | Rock | T |  | 2024/05/29 | 2024/05/28 | 2024/05/29 | 2024/05/29 | DD Internal | Matt | NO | FY22_3B | 2024/02/10 | TODO: Validation
10230001 | 1, 2 | Blackbird-Soldier | T |  | 2024/08/20 | 2024/08/06 | 0000/00/00 | 0000/00/00 | Phase 1 | Erika | NO | FY22_3B | 2024/08/01 | TODO: PBL, BFE, Validation
10230006 | 1, 2 | Big Papillion-Mosquito | T |  | 2024/08/05 | 2024/08/06 | 0000/00/00 | 0000/00/00 | Phase 1 | Reina | YES | FY22_3B | 2024/05/12 | TODO: PBL, BFE, Validation
10170203 | All on MM | Lower Big Sioux | T |  | 2024/03/30 | 2024/05/24 | 2024/06/26 | 2024/05/24 | DD Internal | Matt | NO | FY22_3B | 2024/02/10 | TODO: Validation
07060003 | All on MM | Grant-Little Maquoketa | F | MT | 2024/01/30 | 2024/03/15 | 2024/06/26 | 2024/05/22 | Pass 1/2 | Erika | NO | FY20_1A | 2023/12/12 | Passed MIP Validation
07080101 | All on MM | Copperas-Duck | F | MT | 2024/03/30 | 2024/04/20 | 2024/04/20 | 2024/05/01 | DD Internal | Reina | YES | FY20_1A | 2024/02/10 | TODO: Validation
07110001 | All on MM | Bear-Wyaconda | T |  | 2024/02/28 | 2024/03/26 | 2024/03/26 | 2026/03/28 | Phase 1 | Reina | YES | FY21_2A | 2024/01/10