## Tracking_Main
Stages Complete | HUC8 | Name | FRP % | FRP Complete | BFE_TODO | PBL_Assign | P01_MM | RAW_Grd_MM | DFIRM_Grd_MM | Addl_Grd_MM | Prod Stage | P01 Analyst | AECOM Tie-in | TO_Area | Model Complete | Notes | Unfinished Grids
6 | 07060001 | Coon-Yellow | 33 | CSLF; | F | QB | 2023/11/30 | 2024/02/23 | 2024/08/20 | 2024/08/20 | Pass 1/2 | Matt | NO | FY20_1A | 2023/10/12 | Passed MIP Validation | All on MM
6 | 07060002 | Upper Iowa | 33 | CSLF; | F | MB | 2023/11/30 | 2024/02/23 | 2024/03/10 | 2024/08/20 | Pass 1/2 | Reina | NO | FY20_1A | 2023/10/12 | Passed MIP Validation | All on MM
6 | 07060004 | Turkey | 33 | CSLF; | F | EC | 2024/05/22 | 2024/04/15 | 2024/08/27 | 2024/05/22 | Pass 1/2 | Multi | NO | FY20_1A | 2023/11/11 | Passed MIP Validation | All on MM
6 | 07060006 | Maquoketa | 33 | CSLF; | F | RK | 2024/05/22 | 2024/05/17 | 2024/05/21 | 2024/05/21 | Pass 1/2 | Multi | NO | FY20_1A | 2023/12/12 | Passed MIP Validation | All on MM
6 | 07080102 | Upper Wapsipinicon | 33 | CSLF; | F | KTG | 2023/12/30 | 2024/04/15 | 2024/08/14 | 2024/05/22 | Pass 1/2 | Matt | YES | FY20_1A | 2023/11/11 | Passed MIP Validation | All on MM
5 | 07080103 | Lower Wapsipinicon | 33 | CSLF; | F | MT | 2024/05/22 | 2024/05/09 | 2024/08/14 | 2024/05/22 | DD Submit | Matt | NO | FY20_1A | 2024/01/10 | TODO: MIP Exception Error | All on MM
2 | 07080105 | South Skunk | 0 | 0 | T |  | 2024/06/03 | 2024/03/05 | 2024/06/17 | 0 | Phase 1 | Erika | YES | FY21_2A | 2023/11/11 | 0 | 2
6 | 07080206 | Lower Cedar | 33 | CSLF; | F | QB | 2024/07/13 | 2024/06/14 | 2024/07/16 | 2024/07/18 | Pass 1/2 | Reina | YES | FY20_1A | 2024/05/31 | Passed MIP Validation | All on MM
2 | 07100006 | North Raccoon | 0 | 0 | T |  | 2024/02/26 | 2024/02/13 | 0 | 0 | Phase 1 | YES | YES | FY21_2A | 2023/08/12 | 0 | 1, 2
2 | 07100007 | South Raccoon | 0 | 0 | T |  | 2023/07/30 | 2023/08/31 | 0 | 0 | Phase 1 | YES | YES | FY21_2A | 2023/06/11 | TODO: RAW, DRAFT, Addl | 1, 2
2 | 07100008 | Lake Red Rock | 0 | 0 | T |  | 2023/12/30 | 2024/03/24 | 0 | 0 | Phase 1 | Reina | YES | FY21_2A | 2023/11/11 | 0 | 1, 2
2 | 07100009 | Lower Des Moines | 0 | 0 | T |  | 2024/08/04 | 2024/08/04 | 0 | 0 | Phase 1 | R+E | YES | FY21_2A | 2024/07/25 | 0 | 1, 2
2 | 10230002 | Floyd | 0 | 0 | T |  | 2024/09/09 | 2024/07/12 | 0 | 0 | Phase 1 | Erika, Reina | NO | FY22_3B | 2024/07/08 | UPDATE: Missing Zone A Phase 1; TODO: PBL, BFE, Validation | 1, 2
3 | 10230003 | Little Sioux | 0 | 0 | T | RK | 2024/08/05 | 2024/08/07 | 0 | 0 | DD Mapping | E + M | YES | FY22_3B | 2024/07/16 | TODO: PBL, BFE, Validation | 1, 2
2 | 10230004 | Monona-Harrison Ditch | 0 | 0 | T |  | 2024/08/01 | 2024/08/01 | 0 | 0 | Phase 1 | Reina | NO | FY22_3B | 2024/03/12 | TODO: PBL, BFE, Validation | 1, 2
2 | 10230005 | Maple | 0 | 0 | T |  | 2024/07/11 | 2024/06/12 | 0 | 0 | Phase 1 | Erika | NO | FY22_3B | 2024/07/08 | TODO: PBL, BFE, Validation | 1, 2
3 | 10230007 | Boyer | 0 | 0 | T |  | 2024/07/30 | 2024/07/30 | 0 | 0 | DD Mapping | Reina | YES | FY22_3B | 2024/07/21 | TODO: PBL, BFE, Validation | 1, 2
6 | 07060005 | Apple-Plum | 33 | CSLF; | F | EC | 2024/02/28 | 2024/04/04 | 2024/04/05 | 2024/04/05 | Pass 1/2 | Erika | NO | FY20_1A | 2024/01/10 | Passed MIP Validation | All on MM
6 | 07080201 | Upper Cedar | 33 | CSLF; | F | RK | 2023/12/30 | 2024/03/15 | 2024/08/15 | 2024/08/19 | Pass 1/2 | Matt | YES | FY20_1A | 2023/11/11 | Passed MIP Validation | All on MM
4 | 10170204 | Rock | 0 | 0 | T |  | 2024/05/29 | 2024/05/28 | 2024/05/29 | 2024/05/29 | DD Internal | Matt | NO | FY22_3B | 2024/02/10 | TODO: Validation | All on MM
2 | 10230001 | Blackbird-Soldier | 0 | 0 | T |  | 2024/08/20 | 2024/08/06 | 0 | 0 | Phase 1 | Erika | NO | FY22_3B | 2024/08/01 | TODO: PBL, BFE, Validation | 1, 2
2 | 10230006 | Big Papillion-Mosquito | 0 | 0 | T |  | 2024/08/05 | 2024/08/06 | 0 | 0 | Phase 1 | Reina | YES | FY22_3B | 2024/05/12 | TODO: PBL, BFE, Validation | 1, 2
4 | 10170203 | Lower Big Sioux | 0 | 0 | T |  | 2024/03/30 | 2024/05/24 | 2024/06/26 | 2024/05/24 | DD Internal | Matt | NO | FY22_3B | 2024/02/10 | TODO: Validation | All on MM
6 | 07060003 | Grant-Little Maquoketa | 33 | CSLF; | F | MT | 2024/01/30 | 2024/03/15 | 2024/06/26 | 2024/05/22 | Pass 1/2 | Erika | NO | FY20_1A | 2023/12/12 | Passed MIP Validation | All on MM
6 | 07080101 | Copperas-Duck | 33 | CSLF; | F | MT | 2024/03/30 | 2024/04/20 | 2024/04/20 | 2024/05/01 | Pass 1/2 | Reina | YES | FY20_1A | 2024/02/10 | Passed MIP Validation | All on MM
2 | 07110001 | Bear-Wyaconda | 0 | 0 | T |  | 2024/02/28 | 2024/03/26 | 2024/03/26 | 2026/03/28 | Phase 1 | Reina | YES | FY21_2A | 2024/01/10 | 0 | All on MM

## Progress_Domains
Prod Stage | Number
Pass 2/2 | 7
Pass 1/2 | 6
DD Submit | 5
DD Internal | 4
DD Mapping | 3
Phase 1 | 2
Mapping In-Progress | 1

## Tracking_Main_values
HUC8 | Name | FRP_Perc_Complete | FRP | BFE_TODO | P02a_Assign | P01_MM | RAW_Grd_MM | DFIRM_Grd_MM | Addl_Grd_MM | Prod Stage | P01 Analyst | AECOM Tie-in | TO_Area | Model Complete | Notes | which_grid
07060001 | Coon-Yellow | 33 | CSLF; | F | QB | 2023/11/30 | 2024/02/23 | 2024/08/20 | 2024/08/20 | Pass 1/2 | Matt | NO | FY20_1A | 2023/10/12 | Passed MIP Validation | All on MM
07060002 | Upper Iowa | 33 | CSLF; | F | MB | 2023/11/30 | 2024/02/23 | 2024/03/10 | 2024/08/20 | Pass 1/2 | Reina | NO | FY20_1A | 2023/10/12 | Passed MIP Validation | All on MM
07060004 | Turkey | 33 | CSLF; | F | EC | 2024/05/22 | 2024/04/15 | 2024/08/27 | 2024/05/22 | Pass 1/2 | Multi | NO | FY20_1A | 2023/11/11 | Passed MIP Validation | All on MM
07060006 | Maquoketa | 33 | CSLF; | F | RK | 2024/05/22 | 2024/05/17 | 2024/05/21 | 2024/05/21 | Pass 1/2 | Multi | NO | FY20_1A | 2023/12/12 | Passed MIP Validation | All on MM
07080102 | Upper Wapsipinicon | 33 | CSLF; | F | KTG | 2023/12/30 | 2024/04/15 | 2024/08/14 | 2024/05/22 | Pass 1/2 | Matt | YES | FY20_1A | 2023/11/11 | Passed MIP Validation | All on MM
07080103 | Lower Wapsipinicon | 33 | CSLF; | F | MT | 2024/05/22 | 2024/05/09 | 2024/08/14 | 2024/05/22 | DD Submit | Matt | NO | FY20_1A | 2024/01/10 | TODO: MIP Exception Error | All on MM
07080105 | South Skunk | 0 |  | T |  | 2024/06/03 | 2024/03/05 | 2024/06/17 |  | Phase 1 | Erika | YES | FY21_2A | 2023/11/11 |  | 2
07080206 | Lower Cedar | 33 | CSLF; | F | QB | 2024/07/13 | 2024/06/14 | 2024/07/16 | 2024/07/18 | Pass 1/2 | Reina | YES | FY20_1A | 2024/05/31 | Passed MIP Validation | All on MM
07100006 | North Raccoon | 0 |  | T |  | 2024/02/26 | 2024/02/13 |  |  | Phase 1 | YES | YES | FY21_2A | 2023/08/12 |  | 1, 2
07100007 | South Raccoon | 0 |  | T |  | 2023/07/30 | 2023/08/31 |  |  | Phase 1 | YES | YES | FY21_2A | 2023/06/11 | TODO: RAW, DRAFT, Addl | 1, 2
07100008 | Lake Red Rock | 0 |  | T |  | 2023/12/30 | 2024/03/24 |  |  | Phase 1 | Reina | YES | FY21_2A | 2023/11/11 |  | 1, 2
07100009 | Lower Des Moines | 0 |  | T |  | 2024/08/04 | 2024/08/04 |  |  | Phase 1 | R+E | YES | FY21_2A | 2024/07/25 |  | 1, 2
10230002 | Floyd | 0 |  | T |  | 2024/09/09 | 2024/07/12 |  |  | Phase 1 | Erika, Reina | NO | FY22_3B | 2024/07/08 | UPDATE: Missing Zone A Phase 1; TODO: PBL, BFE, Validation | 1, 2
10230003 | Little Sioux | 0 |  | T | RK | 2024/08/05 | 2024/08/07 |  |  | DD Mapping | E + M | YES | FY22_3B | 2024/07/16 | TODO: PBL, BFE, Validation | 1, 2
10230004 | Monona-Harrison Ditch | 0 |  | T |  | 2024/08/01 | 2024/08/01 |  |  | Phase 1 | Reina | NO | FY22_3B | 2024/03/12 | TODO: PBL, BFE, Validation | 1, 2
10230005 | Maple | 0 |  | T |  | 2024/07/11 | 2024/06/12 |  |  | Phase 1 | Erika | NO | FY22_3B | 2024/07/08 | TODO: PBL, BFE, Validation | 1, 2
10230007 | Boyer | 0 |  | T | MT | 2024/07/30 | 2024/07/30 |  |  | DD Mapping | Reina | YES | FY22_3B | 2024/07/21 | TODO: PBL, BFE, Validation | 1, 2
07060005 | Apple-Plum | 33 | CSLF; | F | EC | 2024/02/28 | 2024/04/04 | 2024/04/05 | 2024/04/05 | Pass 1/2 | Erika | NO | FY20_1A | 2024/01/10 | Passed MIP Validation | All on MM
07080201 | Upper Cedar | 33 | CSLF; | F | RK | 2023/12/30 | 2024/03/15 | 2024/08/15 | 2024/08/19 | Pass 1/2 | Matt | YES | FY20_1A | 2023/11/11 | Passed MIP Validation | All on MM
10170204 | Rock | 0 |  | T |  | 2024/05/29 | 2024/05/28 | 2024/05/29 | 2024/05/29 | DD Internal | Matt | NO | FY22_3B | 2024/02/10 | TODO: Validation | All on MM
10230001 | Blackbird-Soldier | 0 |  | T |  | 2024/08/20 | 2024/08/06 |  |  | Phase 1 | Erika | NO | FY22_3B | 2024/08/01 | TODO: PBL, BFE, Validation | 1, 2
10230006 | Big Papillion-Mosquito | 0 |  | T |  | 2024/08/05 | 2024/08/06 |  |  | Phase 1 | Reina | YES | FY22_3B | 2024/05/12 | TODO: PBL, BFE, Validation | 1, 2
10170203 | Lower Big Sioux | 0 |  | T |  | 2024/03/30 | 2024/05/24 | 2024/06/26 | 2024/05/24 | DD Internal | Matt | NO | FY22_3B | 2024/02/10 | TODO: Validation | All on MM
07060003 | Grant-Little Maquoketa | 33 | CSLF; | F | MT | 2024/01/30 | 2024/03/15 | 2024/06/26 | 2024/05/22 | Pass 1/2 | Erika | NO | FY20_1A | 2023/12/12 | Passed MIP Validation | All on MM
07080101 | Copperas-Duck | 33 | CSLF; | F | MT | 2024/03/30 | 2024/04/20 | 2024/04/20 | 2024/05/01 | Pass 1/2 | Reina | YES | FY20_1A | 2024/02/10 | Passed MIP Validation | All on MM
07110001 | Bear-Wyaconda | 0 |  | T |  | 2024/02/28 | 2024/03/26 | 2024/03/26 | 2026/03/28 | Phase 1 | Reina | YES | FY21_2A | 2024/01/10 |  | All on MM