## Tracking_Main
HUC8 | FRP | P02a_Assign | P01_MM | Name | RAW_Grd_MM | DFIRM_Grd_MM | Addl_Grd_MM | Prod Stage | P01 Analyst | AECOM Tie-in | TO_Area | Model Complete | Notes | which_grid | Addl_Gri_1 | FRP_Perc_Complete
07060001 | WSE/Depth; CSLF; PAC; Velocity | QB | 11/30/2023 | Coon-Yellow | 2024/02/23 | 2024/08/20 | 2024/08/20 | Pass 2/2 | Matt |  | FY20_1A | 10/12/2023 | Passed MIP Validation | All on MM | 2024/08/20 | 100
07060002 | WSE/Depth; CSLF; PAC; Velocity | MB | 11/30/2023 | Upper Iowa | 2024/02/23 | 2024/03/10 | 2024/08/20 | Pass 2/2 | Reina |  | FY20_1A | 10/12/2023 | Passed MIP Validation | All on MM | 2024/08/20 | 100
07060004 | WSE/Depth; CSLF; PAC; Velocity | EC | 5/22/2024 | Turkey | 2024/04/15 | 2024/08/27 | 2024/05/22 | Pass 2/2 | Multi |  | FY20_1A | 11/11/2023 | Passed MIP Validation | All on MM | 2024/05/22 | 100
07060006 | WSE/Depth; CSLF; PAC; Velocity | RK | 5/22/2024 | Maquoketa | 2024/05/17 | 2024/05/21 | 2024/05/21 | Pass 2/2 | Multi |  | FY20_1A | 12/12/2023 | Passed MIP Validation | All on MM | 2024/05/21 | 100
07080102 | WSE/Depth; CSLF; PAC; Velocity | KTG | 12/30/2023 | Upper Wapsipinicon | 2024/04/15 | 2024/08/14 | 2024/05/22 | Pass 2/2 | Matt |  | FY20_1A | 11/11/2023 | Passed MIP Validation | All on MM | 2024/05/22 | 100
07080103 | WSE/Depth; CSLF; PAC; Velocity | MT | 5/22/2024 | Lower Wapsipinicon | 2024/05/09 | 2024/08/14 | 2024/05/22 | Pass 2/2 | Matt |  | FY20_1A | 1/10/2024 | Passed MIP Validation | All on MM | 2024/05/22 | 100
07080105 |  |  | 6/3/2024 | South Skunk | 2024/03/05 | 2024/06/17 |  | Phase 1 | Erika |  | FY21_2A | 11/11/2023 |  | 2 |  | 0
07080206 | WSE/Depth; CSLF; PAC; Velocity | QB | 7/13/2024 | Lower Cedar | 2024/06/14 | 2024/07/16 | 2024/07/18 | Pass 2/2 | Reina |  | FY20_1A | 5/31/2024 | Passed MIP Validation | All on MM | 2024/07/18 | 100
07100006 |  |  | 2/26/2024 | North Raccoon | 2024/02/13 |  |  | Phase 1 | YES |  | FY21_2A | 8/12/2023 |  | 1, 2 |  | 0
07100007 |  |  | 7/30/2023 | South Raccoon | 2023/08/31 |  |  | Phase 1 | YES |  | FY21_2A | 6/11/2023 | TODO: RAW, DRAFT, Addl | 1, 2 |  | 0
07100008 |  |  | 12/30/2023 | Lake Red Rock | 2024/03/24 |  |  | Phase 1 | Reina |  | FY21_2A | 11/11/2023 |  | 1, 2 |  | 0
07100009 |  |  | 8/4/2024 | Lower Des Moines | 2024/08/04 |  |  | Phase 1 | R+E |  | FY21_2A | 7/25/2024 |  | 1, 2 |  | 0
10230002 |  | KTG | 9/9/2024 | Floyd | 2024/07/12 | 2024/09/10 | 2024/09/12 | Pass 1/2 | Erika, Reina |  | FY22_3B | 7/8/2024 | Passed MIP Validation | All on MM | 2024/09/12 | 0
10230003 |  | RK | 8/5/2024 | Little Sioux | 2024/08/07 | 2024/10/15 | 2024/10/15 | Pass 1/2 | E + M |  | FY22_3B | 7/16/2024 | Passed MIP Validation | 1, 2 | 2024/10/15 | 0
10230004 |  | MT | 8/1/2024 | Monona-Harrison Ditch | 2024/08/01 | 2024/10/07 | 2024/10/10 | Pass 1/2 | Reina |  | FY22_3B | 3/12/2024 | MIP Validation Passed | 1, 2 | 2024/10/10 | 0
10230005 |  | RK | 7/11/2024 | Maple | 2024/06/12 |  |  | Pass 1/2 | Erika |  | FY22_3B | 7/8/2024 | MIP Exception | 1, 2 |  | 0
10230007 |  | MT | 7/30/2024 | Boyer | 2024/07/30 |  |  | Pass 1/2 | Reina |  | FY22_3B | 7/21/2024 | Passed MIP Validation | 1, 2 |  | 0
07060005 | WSE/Depth; CSLF; PAC; Velocity | EC | 2/28/2024 | Apple-Plum | 2024/04/04 | 2024/04/05 | 2024/04/05 | Pass 2/2 | Erika |  | FY20_1A | 1/10/2024 | TODO: Missing 0.2% Vel grid | All on MM | 2024/04/05 | 100
07080201 | WSE/Depth; CSLF; PAC; Velocity | RK | 12/30/2023 | Upper Cedar | 2024/03/15 | 2024/08/15 | 2024/08/19 | Pass 2/2 | Matt |  | FY20_1A | 11/11/2023 | Passed MIP Validation | All on MM | 2024/08/19 | 100
10170204 |  |  | 5/29/2024 | Rock | 2024/05/28 | 2024/05/29 | 2024/05/29 | Pass 1/2 | Matt |  | FY22_3B | 2/10/2024 | Passed MIP Validation | All on MM | 2024/05/29 | 0
10230001 |  | RK | 8/20/2024 | Blackbird-Soldier | 2024/08/06 | 2024/10/10 | 2024/10/10 | Pass 1/2 | Erika |  | FY22_3B | 8/1/2024 | Passed MIP Validation | 1, 2 | 2024/10/10 | 0
10230006 |  | RK | 8/5/2024 | Big Papillion-Mosquito | 2024/08/06 | 2024/10/07 | 2024/10/08 | Pass 1/2 | Reina |  | FY22_3B | 5/12/2024 | Passed MIP Validation | All on MM | 2024/10/08 | 0
10170203 |  |  | 3/30/2024 | Lower Big Sioux | 2024/05/24 | 2024/06/26 | 2024/05/24 | Pass 1/2 | Matt |  | FY22_3B | 2/10/2024 | Passed MIP Validation | All on MM | 2024/05/24 | 0
07060003 | WSE/Depth; CSLF; PAC; Velocity | MT | 1/30/2024 | Grant-Little Maquoketa | 2024/03/15 | 2024/06/26 | 2024/05/22 | Pass 2/2 | Erika |  | FY20_1A | 12/12/2023 | Passed MIP Validation | All on MM | 2024/05/22 | 100
07080101 | WSE/Depth; CSLF; PAC; Velocity | MT | 3/30/2024 | Copperas-Duck | 2024/04/20 | 2024/04/20 | 2024/05/01 | Pass 2/2 | Reina |  | FY20_1A | 2/10/2024 | Passed MIP Validation | All on MM | 2024/05/01 | 100
07110001 |  |  | 2/28/2024 | Bear-Wyaconda | 2024/03/26 | 2024/03/26 | 2026/03/28 | Phase 1 | Reina |  | FY21_2A | 1/10/2024 |  | All on MM | 2026/03/28 | 0

## Tracking_Main_values
HUC8 | Draft_MIP | FP_MIP | FRP | BFE_TODO | P02a_Assign | P01_MM | Hydra_MIP | which_grid | Name | Has AECOM Tie | RAW_Grd_MM | DFIRM_Grd_MM | Addl_Grd_MM | Prod Stage | P01 Analyst | TO_Area | Model Complete | Notes | MIP_Case | FRP_Perc_Complete
07060001 | Approved | Submitted | WSE/Depth; CSLF; PAC; Velocity | F | QB | 2023/11/30 | Approved | All on MM | Coon-Yellow | NO | 2024/02/23 | 2024/08/20 | 2024/08/20 | Pass 2/2 | Matt | FY20_1A | 2023/10/12 | Passed MIP Validation | 21-07-0002S | 100
07060002 | Submitted | Submitted | WSE/Depth; CSLF; PAC; Velocity | F | MB | 2023/11/30 | Submitted | All on MM | Upper Iowa | NO | 2024/02/23 | 2024/03/10 | 2024/08/20 | Pass 1/2 | Reina | FY20_1A | 2023/10/12 | Passed MIP Validation; Round 2 Validation 10/11/2024 | 21-07-0002S | 100
07060004 | Approved | Submitted | WSE/Depth; CSLF; PAC; Velocity | F | EC | 2024/05/22 | Submitted | All on MM | Turkey | NO | 2024/04/15 | 2024/08/27 | 2024/05/22 | Pass 2/2 | Multi | FY20_1A | 2023/11/11 | Passed MIP Validation | 21-07-0002S | 100
07060006 | Submitted | Submitted | WSE/Depth; CSLF; PAC; Velocity | F | RK | 2024/05/22 | Submitted | All on MM | Maquoketa | NO | 2024/05/17 | 2024/05/21 | 2024/05/21 | Pass 1/2 | Multi | FY20_1A | 2023/12/12 | Passed MIP Validation; Round 2 Validation 10/11/2024 | 21-07-0002S | 100
07080102 | Approved | Submitted | WSE/Depth; CSLF; PAC; Velocity | F | KTG | 2023/12/30 | Submitted | All on MM | Upper Wapsipinicon | YES | 2024/04/15 | 2024/08/14 | 2024/05/22 | Pass 2/2 | Matt | FY20_1A | 2023/11/11 | Passed MIP Validation | 21-07-0002S | 100
07080103 | Submitted | Submitted | WSE/Depth; CSLF; PAC; Velocity | F | MT | 2024/05/22 | Submitted | All on MM | Lower Wapsipinicon | NO | 2024/05/09 | 2024/08/14 | 2024/05/22 | Pass 1/2 | Matt | FY20_1A | 2024/01/10 | Passed MIP Validation; Round 2 Validation 10/11/2024 | 21-07-0002S | 100
07080105 | Next | Next |  | T |  | 2024/06/03 | Next | 2 | South Skunk | YES | 2024/03/05 | 2024/06/17 |  | Phase 1 | Erika | FY21_2A | 2023/11/11 |  | 22-07-0035S | 0
07080206 | Submitted | Submitted | WSE/Depth; CSLF; PAC; Velocity | F | QB | 2024/07/13 | Submitted | All on MM | Lower Cedar | YES | 2024/06/14 | 2024/07/16 | 2024/07/18 | Pass 1/2 | Reina | FY20_1A | 2024/05/31 | Passed MIP Validation; Round 2 Validation 10/11/2024 | 21-07-0002S | 100
07100006 | Next | Next |  | T |  | 2024/02/26 | Next | 1, 2 | North Raccoon | YES | 2024/02/13 |  |  | Phase 1 | YES | FY21_2A | 2023/08/12 |  | 22-07-0035S | 0
07100007 | Next | Next |  | T |  | 2023/07/30 | Next | 1, 2 | South Raccoon | YES | 2023/08/31 |  |  | Phase 1 | YES | FY21_2A | 2023/06/11 | TODO: RAW, DRAFT, Addl | 22-07-0035S | 0
07100008 | Next | Next |  | T |  | 2023/12/30 | Next | 1, 2 | Lake Red Rock | YES | 2024/03/24 |  |  | Phase 1 | Reina | FY21_2A | 2023/11/11 |  | 22-07-0035S | 0
07100009 | Next | Next |  | T |  | 2024/08/04 | Next | 1, 2 | Lower Des Moines | YES | 2024/08/04 |  |  | Phase 1 | R+E | FY21_2A | 2024/07/25 |  | 22-07-0035S | 0
10230002 | In Backcheck | In-Progress | WSE/Depth; CSLF | F | KTG | 2024/09/09 | In-Progress | All on MM | Floyd | NO | 2024/07/12 | 2024/09/10 | 2024/09/12 | Pass 1/2 | Erika, Reina | FY22_3B | 2024/07/08 | All Hydraulics Spatial Files uploaded 10/16 | 23-07-0037S | 50
10230003 | In Backcheck | In-Progress | WSE/Depth | F | RK | 2024/08/05 | In-Progress | All on MM | Little Sioux | YES | 2024/08/07 | 2024/10/15 | 2024/10/15 | Pass 1/2 | E + M | FY22_3B | 2024/07/16 | All Hydraulics Spatial Files uploaded 10/16 | 23-07-0037S | 25
10230004 | Approved | In-Progress | WSE/Depth; CSLF | F | MT | 2024/08/01 | In-Progress | All on MM | Monona-Harrison Ditch | NO | 2024/08/01 | 2024/10/07 | 2024/10/10 | Pass 1/2 | Reina | FY22_3B | 2024/03/12 | All Hydraulics Spatial Files uploaded 10/16 | 23-07-0037S | 50
10230005 | Approved | In-Progress | WSE/Depth; CSLF | F | RK | 2024/07/11 | In-Progress | All on MM | Maple | NO | 2024/06/12 | 2024/10/16 | 2024/10/16 | Pass 1/2 | Erika | FY22_3B | 2024/07/08 | MIP Exception; All Hydraulics Spatial Files uploaded 10/16 | 23-07-0037S | 50
10230007 | Submitted | In-Progress | WSE/Depth | F | MT | 2024/07/30 | In-Progress | All on MM | Boyer | YES | 2024/07/30 | 2024/10/15 | 2024/10/15 | Pass 1/2 | Reina | FY22_3B | 2024/07/21 | All Hydraulics Spatial Files uploaded 10/16 | 23-07-0037S | 25
07060005 | Approved | Submitted | WSE/Depth; CSLF; PAC; Velocity | F | EC | 2024/02/28 | Approved | All on MM | Apple-Plum | NO | 2024/04/04 | 2024/04/05 | 2024/04/05 | Pass 2/2 | Erika | FY20_1A | 2024/01/10 | TODO: Missing 0.2% Vel grid | 21-07-0002S | 100
07080201 | Approved | Submitted | WSE/Depth; CSLF; PAC; Velocity | F | RK | 2023/12/30 | Submitted | All on MM | Upper Cedar | YES | 2024/03/15 | 2024/08/15 | 2024/08/19 | Pass 2/2 | Matt | FY20_1A | 2023/11/11 | Passed MIP Validation | 21-07-0002S | 100
10170204 | Submitted | In-Progress |  | F |  | 2024/05/29 | In-Progress | All on MM | Rock | NO | 2024/05/28 | 2024/05/29 | 2024/05/29 | Pass 1/2 | Matt | FY22_3B | 2024/02/10 | All Hydraulics Spatial Files uploaded 10/16 | 23-07-0036S | 0
10230001 | Submitted | In-Progress | WSE/Depth; CSLF | F | RK | 2024/08/20 | In-Progress | All on MM | Blackbird-Soldier | NO | 2024/08/06 | 2024/10/10 | 2024/10/10 | Pass 1/2 | Erika | FY22_3B | 2024/08/01 | All Hydraulics Spatial Files uploaded 10/16 | 23-07-0037S | 50
10230006 | Submitted | In-Progress | WSE/Depth; CSLF; PAC; Velocity | F | RK | 2024/08/05 | In-Progress | All on MM | Big Papillion-Mosquito | YES | 2024/08/06 | 2024/10/07 | 2024/10/08 | Pass 1/2 | Reina | FY22_3B | 2024/05/12 | All Hydraulics Spatial Files uploaded 10/16 | 23-07-0037S | 100
10170203 | Submitted | In-Progress |  | F |  | 2024/03/30 | In-Progress | All on MM | Lower Big Sioux | NO | 2024/05/24 | 2024/06/26 | 2024/05/24 | Pass 1/2 | Matt | FY22_3B | 2024/02/10 | All Hydraulics Spatial Files uploaded 10/16 | 23-07-0036S | 0
07060003 | Approved | Submitted | WSE/Depth; CSLF; PAC; Velocity | F | MT | 2024/01/30 | In Backcheck | All on MM | Grant-Little Maquoketa | NO | 2024/03/15 | 2024/06/26 | 2024/05/22 | Pass 2/2 | Erika | FY20_1A | 2023/12/12 | Passed MIP Validation | 21-07-0002S | 100
07080101 | Approved | Submitted | WSE/Depth; CSLF; PAC; Velocity | F | MT | 2024/03/30 | Approved | All on MM | Copperas-Duck | YES | 2024/04/20 | 2024/04/20 | 2024/05/01 | Pass 2/2 | Reina | FY20_1A | 2024/02/10 | Passed MIP Validation | 21-07-0002S | 100
07110001 | Next | Next |  | T |  | 2024/02/28 | Next | All on MM | Bear-Wyaconda | YES | 2024/03/26 | 2024/03/26 | 2024/03/26 | Phase 1 | Reina | FY21_2A | 2024/01/10 |  | 22-07-0035S | 0